## Sheet1
Date	Day of Week	Time	Hours Logged	Endings	Graves	Mariage	MoEML	Moses
2016-05-01	Sun	10:00-11:00	1				Continued copy-editing updated media.xml document.
2016-05-02	Mon	8:30-16:30	8				Finished copy-editing updated media.xml document.; replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts.
2016-05-03	Tues	9:15-16:45	7.5				Replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts.
2016-05-04	Wed	9:00-13:20 & 13:50-16:30	7				Replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts; encoded dates and bibl tags in HYDE1.xml stub; changed status of HYDE1.xml stub to “assigned”; added HOUL1 to PERS1.xml.
2016-05-05	Thurs	8:30-16:30	8				Developed spreadsheet for recording dramatic extracts; fixed typos in BIBL1.xml and RAMA1.xml (as noticed by JJ and KT).
2016-05-06	Fri	8:30-15:30	7				Finished developing spreadsheet for recording dramatic extracts; met with JT and MDH re: static build.
2016-05-07	Sat	20:15-21:15	1				Began writing documentation for external contributors who are recording dramatic extracts.
2016-05-09	Mon	8:30-14:00 & 14:30-16:30	7.5				Researched “The Sign of the Three Feathers” in Bishopsgate Street for user named Alston Jones; continued writing documentation for external contributors who are recording dramatic extracts.
2016-05-10	Tues	9:15-16:30	7.25				Continued writing documentation for external contributors who are recording dramatic extracts; filled out worklog and timesheet; met with JJ re: accounts for timesheets; met with JT, MDH, and JJ re: using @resp attribute as a way to proof persons and locations mentioned in Stow.
2016-05-11	Wed	8:45-16:30	7.75				Continued writing documentation for external contributors who are recording dramatic extracts; encoded new documentation that I finished writing; met with JT and MDH re: GLOSS1 output, new @resp attribute system, and ways of cleaning up @xml:ids; met with JB re: missing Stow work.
2016-05-14	Sat	9:25-11:25; 12:15-13:15, 15:45-19:00	6.25		Responded to MDH and EGW email about work on Graves diary.		Answered MoEML emails; began merging JB's unversioned copy of stow_1598.xml with the copy on SVN.
2016-05-15	Sun	09:00-15:45	6.75				Finished merging JB's unversioned copy of stow_1598.xml with the copy on SVN.
2016-05-18	Wed	6:15-9:30, 10:30-11:00, 13:00-16:30, & 22:00-22:15	7.5				Answered MoEML emails; read through CURT2.xml to identify places where The Curtain is referred to as polygonal.
2016-05-19	Thurs	7:15-9:15, 12:00-15:30, 16:30-17:00, 21:00-22:30	7.5				Re-wrote and copy-edited documentation for dramatic extracts; answered MoEML emails.
2016-05-20	Fri	8:00-9:00, 13:00-16:15-19:30	7.5				Continued writing documentation for encoding persons; researched reference to "Powlters" in WEST14; answered MoEML emails.
2016-05-21	Sat	6:30-9:15, 10:30-12:30, 15:30-16:00, & 16:30-18:45	7.5				Finished researching reference to "Powlters" in WEST14 and corrected broken tag; added new generic location POUL4.xml; emailed JT re: WEST14; continued writing documentation for encoding persons.
2016-05-22	Sun	7:15-9:30, 10:50-11:20, 12:00-16:00, 18:00-18:45	7.5				Finished writing documentation for encoding persons; began encoding documentation for encoding persons (encode_persons.xml).
2016-05-23	Mon		STAT
2016-05-24	Tues	8:30-16:00	7.5				Finished encoding encode_persons.xml; met with CD, KT, and JT for persathon; organized Asana tasks.
2016-05-25	Wed	8:30-14:00 & 14:30-16:30	7.5				Finished copy-editing leftover entries in PERS1.xml from Tuesday's persathon; added new entries to PERS1.xml that had relations with entries from the persathon.
2016-05-26	Thurs	8:30-15:30	7				Began revising documentation for encoding persons based on feedback from JT and CD; met with JJ to copy-edit documentation for preparing a selection of dramatic extracts; began writing document about conventions for diplomatic transcriptions based off of the editorial declaration for mayoral shows; changed my bio statement in PERS1.xml.
2016-05-27	Fri	8:30-16:30	8				Finished writing document about conventions for diplomatic transcriptions; added TAYL14 to list of student team members in team.xml; added BOPA1 and ROBE6 to list of alumni in team.xml; replaced years with job titles in the list of student team members; at the request of JJ, gave myself credit as dtm in all .xml files in SVN and eXist; edited table of contents in about.xml; added link to Museum of London video in LOND2.xml; added new item to list of links in media.xml.
2016-05-30	Mon	8:30-14:45, 16:00-16:15, & 17:00-18:00	7.5	Met with JT and JJ re: new FAST code from Endings for timesheets.			Began encoding WALL2.xml.
2016-05-31	Tues	9:00-10:30 & 11:00-17:00	7.5				Continued encoding WALL2.xml (and gave up due to concerns about the quality of the article); emailed KT re: concerns about WALL2.xml.
2016-06-01	Wed	8:30-11:00 &11:30-16:30	8		Met with MDH re: introduction to Graves Diary project		Cleaned up Asana tasks; began fact-checking MAPS1.xml; began writing XSLT for alphabetizing GLOSS1.xml.
2016-06-02	Thurs	10:30-17:00	6.5		Researched Robert Graves for Graves diary project.		Continued writing XSLT for alphabetizing GLOSS1.xml; team meeting; updated worklog.
2016-06-03	Fri	9:00-17:00	8		Researched Robert Graves for Graves diary project read February 1935 entries in Graves diary project (to familiarize myself with names, places, etc.); worked on missing or broken refs in Graves.		Finished writing XSLT for alphabetizing GLOSS1.xml.
2016-06-06	Mon	8:30-10:30 & 13:30-17:00	5.5		Worked on missing or broken refs in Graves.		Continued writing documentation on researching people; met with JT re: documentation for encoding dates and article about MoEML dates; met with JT re: XSLT for alphabetizing GLOSS1.xml.
2016-06-07	Tues	8:30-16:30	8		Worked on missing or broken refs in Graves.		Added new contributors from EEBO-TCP to PERS1.xml; met with JJ re: revisions for diplomatic_transcriptions.xml and prepare_dramatic_extracts.xml; encoded links to diplomatic_transcriptions.xml and prepare_dramatic_extracts.xml in contribute.xml and praxis.xml.
2016-06-08	Wed	9:30-12:30 & 13:30-18:15	7.75		Worked on missing or broken refs in Graves.		Shared spreadsheet for dramatic extracts with mapoflondon@gmail.com and made mapoflondon the "owner"; created new spreadsheet specifically for dramatic extracts from Hyde Park; emailed Mark Houlahan re: his contribution of dramatic extracts from Hyde Park.
2016-06-09	Thurs	8:45-13:00 & 14:00-17:45	8		Worked on missing or broken refs in Graves.		Spoke with MDH on the phone about agas_instructions.xml; wrote new instructions for mapping toponyms in a library text (in agas_instructions.xml); encoded new link to agas_instructions.xml in map.xml.
2016-06-10	Fri	9:15-13:00 & 14:00-17:15	7		Worked on missing or broken refs in Graves.		Encoded link to agas_instructions.xml in the teaching.xml landing page.
2016-06-11	Sat	8:40-9:55	1.25		Worked on missing or broken refs in Graves.
2016-06-13	Mon	9:00-13:00, 13:30-17:00, 19:45-20:15	8		Worked on refs in Graves with an incorrect @type value.
2016-06-14	Tues	9:45-12:00 & 13:00-17:15	6.5		Worked on refs in Graves with an incorrect @type value;		Met with JT and MDH re: use of <hi> and <foreign> in stow_1598.xml; began writing email to MoEML team about my time off.
2016-06-15	Wed	9:30-17:00 & 17:45-18:15	8	Transposed my MoEML work log for May 2016 and June 1-15 into this new Endings work log; met with JT and MDH re: setting up git repository.	Finished working on refs in Graves with an incorrect @type value; emailed EGW about progress in Graves.		Emailed MoEML team about my work schedule for the end of June and July 2016; met with KT and JT re: workflow for PPP contributions.
2016-06-16	Thurs	9:00-17:00	8		Received email reply from EGW.		Cleaned up and replied to Asana taks; added articles by Edward Bonahue to BIBL1.xml; added instructions for line breaks in prepare_dramatic_extracts.xml; corrected errors in diplomatic_transcriptions.xml; began encoding BEAR1.xml; met with JJ and KT re: DiD grant.
2016-06-17	Fri	8:00-10:00 & 10:30-15:00	6.5	Helped JJ give MC a tour of the Agas map.	Replied to EGW's email.		Continued encoding BEAR1.xml; reviewed recent emails related to the MoEML static build.
2016-06-18	Sat	11:30-12:00	0.5				Began adding index terms to encode_persons.xml; continued encoding BEAR1.xml.
2016-06-20	Mon	8:45-14:00 & 14:30-18:15	8				Finished adding index terms to encode_persons.xml; began writing documentation on researching people; continued encoding BEAR1.xml.
2016-06-21	Tues	8:45-9:45, 9:55-14:10, & 21:45-22:30	6				Continued encoding BEAR1.xml.
2016-06-22	Wed	8:30-9:30, 10:00-11:00, 12:30-13:30, 14:00-15:00, 18:15-19:15, 20:30-23:30	8				Continued encoding BEAR1.xml.
2016-06-23	Thurs	9:00-17:00	8				Emailed Colleen McClintock (MoEML contributor) a copy of the PERS Spreadhseet; continued encoding BEAR1.xml.
2016-07-25	Sun	7:15-12:45 & 12:55-13:55	6.5				Began fact checking and copy-editing MAPS1.xml.
2016-06-27	Mon	10:10-10:55, 15:30-19:00, 21:15-23:30	6.5				Continued encoding BEAR1.xml.
2016-06-28	Tues	7:50-10:15, 11:30-11:45, 12:25-12:40, 13:00-14:45, 16:50-18:35, 21:00-22:05	7.5				Continued encoding BEAR1.xml.
2016-06-29	Wed	8:30-16:30	8	Updated Endings work log from my own records.			Met with JT re: issue with ordinals in ids.xml; finished encoding BEAR1.xml; worked on resolving errors in BEAR1.xml, BIBL1.xml, and PERS1.xml that were “breaking the build;” attended to diagnostics issues that I was responsible for; searched Folger LUNA database for images for BEAR1.xml.
2016-06-30	Thurs	9:15-10:15, 10:45-12:00, 12:15-16:30, 17:20-18:20, 23:30-0:00	8		6.56		Continued writing documentation for researching people in encode_persons.xml; continued fact-checking and copy-editing MAPS1.xml.
2016-07-01	Fri	STAT	7.5
2016-07-04	Mon	8:30-10:30 & 11:00-16:30	7.5				Continued fact-checking and copy-editing MAPS1.xml; met with JJ re: back logged emails and MAPS1.xml workflow; searched for and prepared images for BEAR1.xml; met with JJ and JT to set up MoEML role-based email accounts.
2016-07-05	Tues	8:30-11:00 & 11:30-17:00	8				Continued encoding BEAR1.xml; prepared images (including descriptions) in BEAR1.xml; created new Swan Alley location file, SWAN10.xml; encoded reference to SWAN10.xml in NEWA1.xml and stow_1598.xml; began writing short stub entry in STMI4.xml.
2016-07-06	Wed	9:00-10:00 & 11:00-17:00	7				Finished encoding BEAR1.xml; continued preparing images (including descriptions) in BEAR1.xml.
2016-07-07	Thurs	16:00-20:00	4				Continued writing and encoding documentation in encode_persons.xml.
2016-07-11	Mon	10:00-11:00	1				Continued writing and encoding documentation in encode_persons.xml.
2016-07-14	Thurs	12:00-16:00	4				Continued writing and encoding documentation in encode_persons.xml.
2016-07-23	Fri	8:30-12:00 & 12:30-16:30	7.5				Finished preparing images in BEAR1.xml; sent BEAR1.xml to KT and JJ for final proofing; made revisions to BEAR1.xml as suggested by KT; reviewed and responded to backlogged MoEML emails; met with MDH and JT re: “extreme” and “normalized” renderings of stow_1598.xml.
2016-07-25	Mon	8:30-16:30	8				Updated work log; fixed validation errors in encode_persons.xml; met with KT re: revisions to BEAR1.xml; made requested revisions to BEAR1.xml; published BEAR1.xml; met with JJ and KT re: adding Stow advisory board members to PERS1.xml and team.xml.
2016-07-26	Tues	8:30-14:30	6				Met with MDH and JT re: validation errors; tried to fix failed build (ended up not being an issue I could solve); added Stow advisory board members (and Julia Merritt) to PERS1.xml and team.xml; edited and encoded bio statement for ARCH2; uploaded photo of ARCH2 (also made B&W, cropped); emailed ARCH9 copy of photo and encoded bio statement; emailed KT re: consulting work for fall; reviewed outstanding Asana tasks.
2016-07-27	Wed	9:00-17:00	8				Met with JJ re: vision for team page; helped JJ write FB post re: 10,000th revision; added Shannon Kelley as first author in BEAR1,xml; updated worklog and submitted timesheet; continued proofing MAPS1.xml; helped JJ clean out the MoEML office.

			1