## Sheet1
	Day of Week	Time	Hours Logged	Endings	Graves	Mariage	MoEML	Moses
2016-05-01	Sun	10:00-11:00	1				Continued copy-editing updated media.xml document.
2016-05-02	Mon	8:30-16:30	8				Finished copy-editing updated media.xml document.; replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts.
2016-05-03	Tues	9:15-16:45	7.5				Replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts.
2016-05-04	Wed	9:00-13:20 & 13:50-16:30	7				Replaced quotes from modern editions in RAMA1.xml with quotes from EEBO texts; encoded dates and bibl tags in HYDE1.xml stub; changed status of HYDE1.xml stub to “assigned”; added HOUL1 to PERS1.xml.
2016-05-05	Thurs	8:30-16:30	8				Developed spreadsheet for recording dramatic extracts; fixed typos in BIBL1.xml and RAMA1.xml (as noticed by JJ and KT).
2016-05-06	Fri	8:30-15:30	7				Finished developing spreadsheet for recording dramatic extracts; met with JT and MDH re: static build.
2016-05-07	Sat	20:15-21:15	1				Began writing documentation for external contributors who are recording dramatic extracts.
2016-05-09	Mon	8:30-14:00 & 14:30-16:30	7.5				Researched “The Sign of the Three Feathers” in Bishopsgate Street for user named Alston Jones; continued writing documentation for external contributors who are recording dramatic extracts.
2016-05-10	Tues	9:15-16:30	7.25				Continued writing documentation for external contributors who are recording dramatic extracts; filled out worklog and timesheet; met with JJ re: accounts for timesheets; met with JT, MDH, and JJ re: using @resp attribute as a way to proof persons and locations mentioned in Stow.
2016-05-11	Wed	8:45-16:30	7.75				Continued writing documentation for external contributors who are recording dramatic extracts; encoded new documentation that I finished writing; met with JT and MDH re: GLOSS1 output, new @resp attribute system, and ways of cleaning up @xml:ids; met with JB re: missing Stow work.
2016-05-14	Sat	9:25-11:25; 12:15-13:15, 15:45-19:00	6.25		Responded to MDH and EGW email about work on Graves diary.		Answered MoEML emails; began merging JB's unversioned copy of stow_1598.xml with the copy on SVN.
2016-05-15	Sun	09:00-15:45	6.75				Finished merging JB's unversioned copy of stow_1598.xml with the copy on SVN.
2016-05-18	Wed	6:15-9:30, 10:30-11:00, 13:00-16:30, & 22:00-22:15	7.5				Answered MoEML emails; read through CURT2.xml to identify places where The Curtain is referred to as polygonal.
2016-05-19	Thurs	7:15-9:15, 12:00-15:30, 16:30-17:00, 21:00-22:30	7.5				Re-wrote and copy-edited documentation for dramatic extracts; answered MoEML emails.
2016-05-20	Fri	8:00-9:00, 13:00-16:15-19:30	7.5				Continued writing documentation for encoding persons; researched reference to "Powlters" in WEST14; answered MoEML emails.
2016-05-21	Sat	6:30-9:15, 10:30-12:30, 15:30-16:00, & 16:30-18:45	7.5				Finished researching reference to "Powlters" in WEST14 and corrected broken tag; added new generic location POUL4.xml; emailed JT re: WEST14; continued writing documentation for encoding persons.
2016-05-22	Sun	7:15-9:30, 10:50-11:20, 12:00-16:00, 18:00-18:45	7.5				Finished writing documentation for encoding persons; began encoding documentation for encoding persons (encode_persons.xml).
2016-05-23	Mon		STAT
2016-05-24	Tues	8:30-16:00	7.5				Finished encoding encode_persons.xml; met with CD, KT, and JT for persathon; organized Asana tasks.
2016-05-25	Wed	8:30-14:00 & 14:30-16:30	7.5				Finished copy-editing leftover entries in PERS1.xml from Tuesday's persathon; added new entries to PERS1.xml that had relations with entries from the persathon.
2016-05-26	Thurs	8:30-15:30	7				Began revising documentation for encoding persons based on feedback from JT and CD; met with JJ to copy-edit documentation for preparing a selection of dramatic extracts; began writing document about conventions for diplomatic transcriptions based off of the editorial declaration for mayoral shows; changed my bio statement in PERS1.xml.
2016-05-27	Fri	8:30-16:30	8				Finished writing document about conventions for diplomatic transcriptions; added TAYL14 to list of student team members in team.xml; added BOPA1 and ROBE6 to list of alumni in team.xml; replaced years with job titles in the list of student team members; at the request of JJ, gave myself credit as dtm in all .xml files in SVN and eXist; edited table of contents in about.xml; added link to Museum of London video in LOND2.xml; added new item to list of links in media.xml.
2016-05-30	Mon	8:30-14:45, 16:00-16:15, & 17:00-18:00	7.5	Met with JT and JJ re: new FAST code from Endings for timesheets.			Began encoding WALL2.xml.
2016-05-31	Tues	9:00-10:30 & 11:00-17:00	7.5				Continued encoding WALL2.xml (and gave up due to concerns about the quality of the article); emailed KT re: concerns about WALL2.xml.
2016-06-01	Wed	8:30-11:00 &11:30-16:30	8		Met with MDH re: introduction to Graves Diary project		Cleaned up Asana tasks; began fact-checking MAPS1.xml; began writing XSLT for alphabetizing GLOSS1.xml.
2016-06-02	Thurs	10:30-17:00	6.5		Researched Robert Graves for Graves diary project.		Continued writing XSLT for alphabetizing GLOSS1.xml; team meeting; updated worklog.
2016-06-03	Fri	9:00-17:00	8		Researched Robert Graves for Graves diary project read February 1935 entries in Graves diary project (to familiarize myself with names, places, etc.); worked on missing or broken refs in Graves.		Finished writing XSLT for alphabetizing GLOSS1.xml.
2016-06-06	Mon	8:30-10:30 & 13:30-17:00	5.5		Worked on missing or broken refs in Graves.		Continued writing documentation on researching people; met with JT re: documentation for encoding dates and article about MoEML dates; met with JT re: XSLT for alphabetizing GLOSS1.xml.
2016-06-07	Tues	8:30-16:30	8		Worked on missing or broken refs in Graves.		Added new contributors from EEBO-TCP to PERS1.xml; met with JJ re: revisions for diplomatic_transcriptions.xml and prepare_dramatic_extracts.xml; encoded links to diplomatic_transcriptions.xml and prepare_dramatic_extracts.xml in contribute.xml and praxis.xml.
2016-06-08	Wed	9:30-12:30 & 13:30-18:15	7.75		Worked on missing or broken refs in Graves.		Shared spreadsheet for dramatic extracts with mapoflondon@gmail.com and made mapoflondon the "owner"; created new spreadsheet specifically for dramatic extracts from Hyde Park; emailed Mark Houlahan re: his contribution of dramatic extracts from Hyde Park.
2016-06-09	Thurs	8:45-13:00 & 14:00-17:45	8		Worked on missing or broken refs in Graves.		Spoke with MDH on the phone about agas_instructions.xml; wrote new instructions for mapping toponyms in a library text (in agas_instructions.xml); encoded new link to agas_instructions.xml in map.xml.
2016-06-10	Fri	9:15-13:00 & 14:00-17:15	7		Worked on missing or broken refs in Graves.		Encoded link to agas_instructions.xml in the teaching.xml landing page.
2016-06-11	Sat	8:40-9:55	1.25		Worked on missing or broken refs in Graves.
2016-06-13	Mon	9:00-13:00, 13:30-17:00, 19:45-20:15	8		Worked on refs in Graves with an incorrect @type value.
2016-06-14	Tues	9:45-12:00 & 13:00-17:15	6.5		Worked on refs in Graves with an incorrect @type value;		Met with JT and MDH re: use of <hi> and <foreign> in stow_1598.xml; began writing email to MoEML team about my time off.
2016-06-15	Wed	9:30-17:00 & 17:45-18:15	8	Transposed my MoEML work log for May 2016 and June 1-15 into this new Endings work log; met with JT and MDH re: setting up git repository.	Finished working on refs in Graves with an incorrect @type value; emailed EGW about progress in Graves.		Emailed MoEML team about my work schedule for the end of June and July 2016; met with KT and JT re: workflow for PPP contributions.
2016-06-16	Thurs	9:00-17:00	8		Received email reply from EGW.		Cleaned up and replied to Asana taks; added articles by Edward Bonahue to BIBL1.xml; added instructions for line breaks in prepare_dramatic_extracts.xml; corrected errors in diplomatic_transcriptions.xml; began encoding BEAR1.xml; met with JJ and KT re: DiD grant.
2016-06-17	Fri	8:00-10:00 & 10:30-15:00	6.5	Helped JJ give MC a tour of the Agas map.	Replied to EGW's email.		Continued encoding BEAR1.xml; reviewed recent emails related to the MoEML static build.
2016-06-18	Sat	11:30-12:00	0.5				Began adding index terms to encode_persons.xml; continued encoding BEAR1.xml.
2016-06-20	Mon	8:45-14:00 & 14:30-18:15	8				Finished adding index terms to encode_persons.xml; began writing documentation on researching people; continued encoding BEAR1.xml.
2016-06-21	Tues	8:45-9:45, 9:55-14:10, & 21:45-22:30	6				Continued encoding BEAR1.xml.
2016-06-22	Wed	8:30-9:30, 10:00-11:00, 12:30-13:30, 14:00-15:00, 18:15-19:15, 20:30-23:30	8				Continued encoding BEAR1.xml.
2016-06-23	Thurs	9:00-17:00	8				Emailed Colleen McClintock (MoEML contributor) a copy of the PERS Spreadhseet; continued encoding BEAR1.xml.
2016-07-25	Sun	7:15-12:45 & 12:55-13:55	6.5				Began fact checking and copy-editing MAPS1.xml.
2016-06-27	Mon	10:10-10:55, 15:30-19:00, 21:15-23:30	6.5				Continued encoding BEAR1.xml.
2016-06-28	Tues	7:50-10:15, 11:30-11:45, 12:25-12:40, 13:00-14:45, 16:50-18:35, 21:00-22:05	7.5				Continued encoding BEAR1.xml.
2016-06-29	Wed	8:30-16:30	8	Updated Endings work log from my own records.			Met with JT re: issue with ordinals in ids.xml; finished encoding BEAR1.xml; worked on resolving errors in BEAR1.xml, BIBL1.xml, and PERS1.xml that were “breaking the build;” attended to diagnostics issues that I was responsible for; searched Folger LUNA database for images for BEAR1.xml.
2016-06-30	Thurs	9:15-10:15, 10:45-12:00, 12:15-16:30, 17:20-18:20, 23:30-0:00	8		6.56		Continued writing documentation for researching people in encode_persons.xml; continued fact-checking and copy-editing MAPS1.xml.
2016-07-01	Fri	STAT	7.5
2016-07-04	Mon	8:30-10:30 & 11:00-16:30	7.5				Continued fact-checking and copy-editing MAPS1.xml; met with JJ re: back logged emails and MAPS1.xml workflow; searched for and prepared images for BEAR1.xml; met with JJ and JT to set up MoEML role-based email accounts.
2016-07-05	Tues	8:30-11:00 & 11:30-17:00	8				Continued encoding BEAR1.xml; prepared images (including descriptions) in BEAR1.xml; created new Swan Alley location file, SWAN10.xml; encoded reference to SWAN10.xml in NEWA1.xml and stow_1598.xml; began writing short stub entry in STMI4.xml.
2016-07-06	Wed	9:00-10:00 & 11:00-17:00	7				Finished encoding BEAR1.xml; continued preparing images (including descriptions) in BEAR1.xml.
2016-07-07	Thurs	16:00-20:00	4				Continued writing and encoding documentation in encode_persons.xml.
2016-07-11	Mon	10:00-11:00	1				Continued writing and encoding documentation in encode_persons.xml.
2016-07-14	Thurs	12:00-16:00	4				Continued writing and encoding documentation in encode_persons.xml.
2016-07-21	Thurs	8:00-10:45 & 14:50-19:05	7				Continued vetting and copy-editing MAPS1.xml (again).
2016-07-22	Fri	9:00-12:00 & 12:30-16:30	7				Finished preparing images in BEAR1.xml; sent BEAR1.xml to KT and JJ for final proofing; made revisions to BEAR1.xml as suggested by KT; reviewed and responded to backlogged MoEML emails; met with MDH and JT re: “extreme” and “normalized” renderings of stow_1598.xml.
2016-07-23	Sat	8:00-11:00 & 12:00-13:00	4				Continued vetting and copy-editing MAPS1.xml.
2016-07-25	Mon	8:30-15:30	7				Updated work log; fixed validation errors in encode_persons.xml; met with KT re: revisions to BEAR1.xml; made requested revisions to BEAR1.xml; published BEAR1.xml; met with JJ and KT re: adding Stow advisory board members to PERS1.xml and team.xml.
2016-07-26	Tues	8:30-14:30	6				Met with MDH and JT re: validation errors; tried to fix failed build (ended up not being an issue I could solve); added Stow advisory board members (and Julia Merritt) to PERS1.xml and team.xml; edited and encoded bio statement for ARCH2; uploaded photo of ARCH2 (also made B&W, cropped); emailed ARCH9 copy of photo and encoded bio statement; emailed KT re: consulting work for fall; reviewed outstanding Asana tasks.
2016-07-27	Wed	9:00-16:30	7.5				Met with JJ re: vision for team page; helped JJ write FB post re: 10,000th revision; added Shannon Kelley as first author in BEAR1,xml; updated worklog and submitted timesheet; continued proofing MAPS1.xml; helped JJ clean out the MoEML office.
2016-07-28	Thurs	9:00-10:30 & 11:00-14:00 & 14:30-16:45	7		Met with JT re: RG vs. RG1 in references.xml		Continued vetting and copy-editing MAPS1.xml; met with MDH re: issue with <supplied> tags with <notes> in <date>s.
2016-07-29	Fri	9:15-13:00 & 13:15-16:30	7		Met with JT re: his improvements to rendering in Graves project.		Continued vetting and copy-editing MAPS1.xml; met with JJ briefly about how to handle early print surrogates in MAPS1.xml.
2016-08-31	Sun	8:00-12:00	4				Continued vetting and copy-editing MAPS1.xml.
2016-08—01	Mon	STAT	5.866666667
2016-08-02	Tues	8:45-14:45, 14:58-15:08, 15:30-15:40, 15:50-16:05, 16:40-17:20, & 17:35-17:50	7.5				Continued vetting and copy-editing MAPS1.xml; continued writing documentation for encoding personography entries for modern contributors.
2016-08-04	Wed	8:45-16:15	7.5				Continued vetting and copy-editing MAPS1.xml; met with KT re: consultant duties in the fall.
2016-08-04	Thurs	8:45-16:15	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-08	Fri	8:30-12:00 &12:30-16:30	7.5		Met with JT re: his improvements to JavaScript and CSS in Graves.		Continued vetting and copy-editing MAPS1.xml.
2016-08-10	Mon	8:45-4:15	7.5				Continued vetting and copy-editing MAPS1.xml; helped JJ move ISE and MoEML office into HCMC.
2016-08-10	Tues	9:00-16:00	7				Continued vetting and copy-editing MAPS1.xml.
2016-08-10	Wed	10:45-15:00 & 15:15-17:00	6				Continued vetting and copy-editing MAPS1.xml.
2016-08-11	Thurs	8:45-13:00 & 13:30-16:45	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-12	Fri	8:45-12:00 & 12:30-16:45	7.5				Prepared and submitted timesheets for Jul 16-31 and Aug 1-15; continued vetting and copy-editing MAPS1.xml.
2016-08-15	Mon	09:00-16:30	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-16	Tues	8:30-16:30	8				Continued vetting and copy-editing MAPS1.xml.
2016-08-17	Wed	8:30-16:30	8				Continued vetting and copy-editing MAPS1.xml; copy-edited JJ's entry re: Mitacs in news.xml.
2016-08-18	Thurs	9:00-17:00	8				Finished vetting and copy-editing MAPS1.xml; met with JJ re: Mitacs image guidelines.
2016-08-19	Fri	8:30-16:30	8				Last few revisions to MAPS1.xml content; began working on XSLT for MAPS1.xml.
2016-08-22	Mon	8:45-16:45	8				Met with JJ re: questions about MAPS1.xml; continued working on XSLT for MAPS1,xml; met with JT re: questions about XSLT.
2016-08-23	Tues	8:30-16:30	8				Began going through Martin's list of unlinked binary documents; continued working on XSLT for MAPS1.xml; met with JJ re: questions about MAPS1.xml; met with JJ and JT re: what we can do with data from DEEP.
2016-08-24	Wed	8:45-13:30, 13:45-15:10, & 16:20-17:15	6.75				Continued working on XSLT for MAPS1.xml database.
2016-08-25	Thurs	8:45-2:00, 2:55-3:05,3:20-3:45, & 4:00-6:10	8		Met with JT re: CSS design for Graves website.		Continued working on XSLT for MAPS1.xml database.
2016-08-26	Fri	8:00-12:45	4.75				Continued working on XSLT for MAPS1.xml database; worked on Millions of Words abstract with JJ; began adding maps from Strype to MAPS1.xml database.
2016-08-29	Mon	8:15-16:45	8.5	Attended Ending meeting.			Continued adding maps from Strype to MAPS1.xml database; worked on Millions of Words with JT.
2016-08-30	Tues	8:30-13:30 & 13:45-16:45	8				Finished adding maps from Strype to MAPS1.xml database.
2016-09-05	Mon	STAT	7.5
2016-09-12	Mon	9:00-4:30	7.5				Designed template for MAPS1.xml database; continued working on XSLT for MAPS1.xml database.
2016-09-16	Fri	8:00-10:45	2.75				Continued working on XSLT for MAPS1.xml database.
2016-09-17	Sat	10:00-12:30	2.5				Added KAET1 to team.xml; edited KAET1 entry in PERS1.xml; changed photo for LAND2 in team.xml.
2016-09-19	Mon	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-20	Tues	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-21	Wed	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-22	Thurs	8:15-9:00	0.75				Continued working on XSLT for MAPS1.xml database.
2016-09-23	Fri	8:30-9:00	0.5				Continued working on XSLT for MAPS1.xml database.
2016-09-26	Mon	n/a	1.8	Extra hours logged here to correct error on previous spreadsheet (approved by JJ and KT).
2016-09-28	Wed	8:00-9:30	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-29	Thurs	8:00-9:00	1				Submited timesheet to MDH; continued working on XSLT for MAPS1.xml database.
2016-09-30	Fri	8:30-10:00	1.5				Updated Endings worklog; continued working on XSLT for MAPS1.xml database.
2016-10-04	Tues	13:30-14:30	1				Continued working on XSLT for MAPS1.xml database.
2016-10-08	Sat	16:00-19:00	3				Continued working on XSLT for MAPS1.xml database.
2016-10-12	Wed	8:00-9:00 & 16:00-18:30	3.5				Continued working on XSLT for MAPS1.xml database.
2016-10-13	Thurs	10:00-12:00	2				Manually edited XML in MAPS1.xml; continued working on XSLT for MAPS1.xml database.
2016-10-14	Fri	12:00-14:30	2.5				Continued working on XSLT for MAPS1.xml database.
2016-10-15	Sat	10:00-12:00 & 14:00-15:00	3				Continued working on XSLT for MAPS1.xml database.
2016-10-16	Mon	15:00-17:00	2	Endings fall meeting.			MoEML team meeting.
2016-10-17	Tues	8:00-8:30`	0.5				Continued working on XSLT for MAPS1.xml database; updated Endings worklog.
2016-10-21	Fri	10:30-11:00 & 17:00-18:00	1.5				Continued working on XSLT for MAPS1.xml database; emailed JJ, KT, and JT re: progress on MAPS1.xml database and follow-up to LBTD stationers.
2016-10-22	Sat	9:30-11:00 & 17:00-17:30	2				Met with JT re: issue in MAPS1.xml XSLT.
2016-10-23	Sun	9:00-10:00	1				Fixed issue with KAET1 bio in PERS1.xml (turns out the entire PERS1.xml file was out of date on eXist).
2016-10-24	Mon	8:10-9:10	1				Continued working on XSLT for MAPS1.xml database.
2016-10-31	Mon	`13:30-14:30	1				Updated Endings worklog; continued working on XSLT for MAPS1.xml database.
2016-11-01	Tues	13:30-14:00	0.5				Continued working on XSLT for MAPS1.xml database.
2016-11-02	Wed	10:00-11:00	1				Continued working on XSLT for MAPS1.xml database.
2016-11-03	Thurs	14:00-15:30	1.5				Made final few changes to XSLT for MAPS1.xml database; emailed JT to schedule phone meeting re: XSLT; reviewed MoEML emails; added new MoEML blog posts to media.xml.
2016-11-04	Fri	15:00-16:30	1.5				Prepared MAPS1 XSLT for JT to review; emailed JT with troubleshooting questions re: MAPS1 XSLT; updated media.xml on eXist; emailed MoEML team re: changes in media.xml.
2016-11-06	Sun	9:00-10:00	1				Began identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-07	Mon	8:30-9:30	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-08	Tues	12:00-13:00	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-09	Wed	8:15-9:15	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-10	Thurs	8:15-9:30	1.25				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-11	Fri	9:00-9:30 & 10:30-11:15	1.25				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-12	Sat	11:00-12:00	1				Uploaded PERS1.xml and team.xml to eXist on JJ's behalf;Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-13	Sun	10:00-11:00	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-14	Mon	8:55-9:25 & 11:00-11:30	1	Updated Endings work log from my own records.			Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-15	Tues	12:30-13:30	1				Added new locations from MAPS1.xml to placeogrpahy; emailed MDH re: issues with schematron in oXygen.
2016-11-16	Wed	9:00-9:45	0.75				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-17	Thurs	9:00-10:00 & 11:00-11:30	1.5				Restored previous versions of PERS1.xml and team.xml (accidentally overwritten); emailed JJ about overwriting issue.
2016-11-18	Fri	10:00-11:00	1				Finished identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy; began looking into ways to clean up extra spaces and character in output of MAPS1_output.xsl.
2016-11-20	Sun	9:00-10:30	1.5				Reviewed JT's email about how to improve MAPS1_output.xsl and experimented with his suggestions; I decided that it would be quicker to clean up the output of MAPS1_output.xsl manually.
2016-11-21	Mon	11:15-12:15	1				Cleaned up the output of MAPS1_output.xsl manually; began copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-22	Tues	12:15-13:15	1	Updated Endings work log from my own records.			Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-23	Wed	9:00-10:00	1				Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-24	Thurs	9:30-10:30	1				Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-25	Fri	8:30-9:30	1				Finished copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates; renamed MAPS1.xml as MAPS1.xml_ and took it off eXist (in order to address duplicate IDs errors); uploaded BIBL1.xml to eXist.
2016-11-26	Sat	9:30-10:30	1				Renamed MAPS1_db.xml as MAPS1.xml; began formatting MAPS1.database before uplaoding it to eXist.
2016-11-27	Sun	9:30-11:00	1.5				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-11-28	Mon	9:00-10:00	1				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-11-29	Tues	8:30-9:30	1	Updated Endings work log from my own records.			Continued formatting MAPS1.database before uplaoding it to eXist; reviewed and responded to email re: MAPS1.xml from JT.
2016-12-01	Thurs	9:00-10:00	1				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-12-02	Fri	10:30-13:00	2.5				Finished formatting MAPS1 database; began adding cartographers to PERS1.xml from MAPS1.xml.
2016-12-05	Mon	10:35:11:35	1				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-06	Tues	11:00-11:45	0.75				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-07	Wed	10:00-11:00	1				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-08	Thurs	10:45-11:00	0.75				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-09	Fri	11:00-11:30	0.5				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-12	Mon	10:00-11:00	1	Emailed Endings team re: issue with overtime pay; updated Endings work log from my own records.
2016-12-16	Fri	9:45-11:00	1.25				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-18	Sun	10:30-11:00	0.5				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-19	Mon	13:00-14:30	1.5				Finished adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates); removed non early modern cartographers from PERS1.xml.
2016-12-20	Tues	8:00-10:00, 13:00-16:30, & 18:30-21:00	8				Began testing external links in MAPS1.xml and correcting them as needed; worked through diagnostics errors for MAPS1.xml, making MAPS1.xml ready for publication.
2016-12-21	Wed	7:30-9:15 & 15:20-16:50	3.25				Finished testing external links in MAPS1.xml and correcting them as needed.
2016-12-22	Thurs	8:30-9:15 & 10:30-10:45	1				Wrote and sent email to MoEML team about next steps for MAPS1.xml.
2016-12-23	Fri	9:35-9:50, 10:20-12:20, 13:00-14:15	3.5				Began copy-editing JT's abstracts for ALDE1, NOBL1, and FOST1.
2016-12-24	Sat	9:30-11:00, 6:15-6:45, 7:10-7:40, 8:45-10:30	4.5	Updated Endings work log from my own records.			Finished copy-editing JT's abstracts for ALDE1, NOBL1, and FOST1; fixed broken file path in SVN by checking out the /london repository again; cleaned up Asana tasks; continued copy editing Roland's WALL2 article after it had been revised by JJ and KT,
2016-12-27	Tues	10:00-10:30	0.5				Began encoding Roland's WALL2.xml.
2016-12-28	Wed	9:00-10:15, 14:00-14:30, & 16:30-17:15	3.5				Continued encoding Roland's WALL2.xml.
2016-12-30	Fri	8:00-9:00	1				Continued encoding Roland's WALL2.xml.
2016-12-31	Sat	13:05-13:20, 14:15-15:45, 16:45-17:00, & 17:30-18:15	2.5				Continued encoding Roland's WALL2.xml; met with JJ about next steps for MAPS1.xml.
2017-01-03	Tues	10:00-11:15 & 22:15-22:45	1.75				Began alphabetizing MAPS1.xml; began writing email to BT about his role in copy editing MAPS1.xml.
2017-01-04	Wed	9:30-10:15, 16:35-17:20, & 18:00-18:30	2				Finished alphabetizing MAPS1.xml; continued writing email to BT about his role in copy editing MAPS1.xml; continued encoding Roland's WALL2.xml.
2017-01-05	Thurs	9:00-9:30 & 17:30-18:00	1				Finished writing email to BT about his role in copy editing MAPS1.xml; continued encoding Roland's WALL2.xml.
2017-01-06	Fri	8:10-10:10 & 17:00-17:15	2.25				Continued encoding Roland's WALL2.xml.
2017-01-07	Sat	10:35-12:35, 19:00-19:45, & 20:20-20:50	3.25				Worked on finding, downloading, and cropping images for WALL2.xml; continued encoding Roland's WALL2.xml.
2017-01-09	Mon	8:50-10:20	1.5	Updated Endings work log from my own records.			Continued encoding and revising section on "literary significance" in Roland's WALL2.xml.
2017-01-10	Tues	8:45-9:45	1				Continued encoding and revising section on "literary significance" in Roland's WALL2.xml.
2017-01-11	Wed	9:50-10:50	1				Continued encoding and revising section on "literary significance" in Roland's WALL2.xml; began encoding graphics in WALL2.xml.
2017-01-12	Thurs	10:00-11:00	1				Continued encoding and revising section on "literary significance" in Roland's WALL2.xml; added new sources to BIBL1.xml from WALL2.xml.
2017-01-14	Sat	10:00-12:00	2				Researched source for "perch (unit)" (had some trouble with fact-checking); continued encoding and revising section on "literary significance" in Roland's WALL2.xml.
2017-01-16	Mon	10:00-11:00	1				Finished encoding WALL2.xml; began adding responsibility statements to WALL2.xml.
2017-01-18	Wed	10:45-11:45	1	Updated Endings work log from my own records.			Continued adding responsibility statements to WALL2.xml; reviewed email from BT about MAPS1.xml.
2017-01-19	Thurs	11:45-12:45 & 16:30-17:30	2				Finished adding responsibility statements to WALL2.xml; began stylizing graphics in WALL2.xml; corresponded with MDH re: duplicate ids.
2017-01-20	Fri	10:00-11:00	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page).
2017-01-21	Sat	8:30-9:30	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page).
2017-01-23	Mon	9:30-10:30	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page).
2017-01-24	Tues	9:00-10:00	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page).
2017-01-25	Wed	9:00-10:00	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page); found and downloaded images of Kentish ragstone and Pyramus/Thisbe for WALL2.xml.
2017-01-26	Thurs	8:30-9:30	1				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page).
2017-01-27	Fri	9:00-10:00 & 13:45-15:15	2.5	Prepared for Endings team meeting; attended Endings team meeting via Skype.			Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page); added images of Kentish ragstone and Pyramus/Thisbe to WALL2.xml.
2017-01-28	Sat	9:30-12:00	2.5				Continued stylizing graphics in WALL2.xml (adjusting margins to fit on page); re-wrote image descriptions because of versioning error.
2017-02-31	Tues	9:30-11:30	2	Updated Endings work log from my own records.			Finished stylizing graphics in WALL2.xml (adjusting margins to fit on page); began reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-01	Wed	11:30-12:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-03	Fri	10:35-11:35	1	Tabulated hours worked as against alloted hours in my contract.			Tried to add Leah Thomas's article to Project CV (it's already there); continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-04	Sat	9:00-10:30	1.5				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-06	Mon	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-07	Tues	8:00-9:00	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-08	Wed	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-09	Thurs	16:20-17:20	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-10	Fri	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database. Identified missing entriesand corrected publication years in MAPS1.xml.
2017-02-11	Sat	10:00-12:30	2.5				Added Catriona Duncan's two presentations and one blog post to project CV; began writing email to JJ and KT re: progress on MAPS1.xml and WALL2.xml.
2017-02-13	Mon	10:30-11:30	1				Finished writing email to JJ and KT re: progress on MAPS1.xml and WALL2.xml; finished reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-14	Tues	9:15-10:55	0.75	Began updating my Endings work log from my own records.
2017-02-15	Wed	10:45-12:00	1.25	Finished updating my Endings work log from my own records.			Standardized spelling of "bird's-eye" in MAPS1.xml. Organized and cleaned-up Asana tasks.
2017-02-17	Fri	8:50-9:50	1				Finished organizing Asana tasks; began copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-18	Sat	10:15-11:00	0.75				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-19	Sun	9:00-10:30 & 14:00-16:30	4				Composed email to JJ and MDH re: concerns about hours worked and records; continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-20	Mon	12:00-12:15	0.25				Sent email to JJ and MDH re: concerns about hours worked and records; added and commited JW's citation guide to SVN.
2017-02-25	Sat	13:50-15:05, 15:35-16:05, 18:50-20:35	3.5	Updated Endings work log from my own records.			Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-26	Sun	9:35-10:35	1				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-27	Mon	16:00-16:45	0.75				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-02-28	Tues	9:00-10:00	1				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-01	Wed	10:45-11:45	1				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-02	Thurs	11:05-13:05	2	Updated Endings work log from my own records.			Reviewed email reply from MDH re: concerns about my MoEML hours and records; continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-04	Sat	9:00-11:30	2.5	Updated Endings work log from my own records.			Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.; created HOTH3.xml as a place holder for David Carnegie's forthcoming article.
2017-03-06	Mon	11:00-11:15	0.25				Sent email to JJ, JT, and MDH re: uploading HOTH3.xml to eXist; sent email to David Carnegie re: HOTH3.xml.
2017-03-07	Tues	10:30-11:45	1.25				Continued copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8 (worked through citations for maps, researched MLA's container system on MLA style gujide webstie).
2017-03-08	Wed	10:15-11:30	1.25				Emaild JT re: Pantzer DH project; finished copy-editing and updating JW's citation guide to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-09	Thurs	10:40-11:55	1.25				Finished copyediting list of works cited in JW's citation style guide; added JW's citation encoding guide to SVN for future work.
2017-03-10	Fri	9:45-11:00	1.25				Began copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-11	Sat	9:25-9:40 & 11:00-12:00	1.25				Continued copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-13	Mon	12:00-13:00	1	Updated Endings work log from my own records.			Continued copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-14	Tues	11:00-12:15	1.25				Continued copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-15	Wed	8:00-9:15	1.25				Continued copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-16	Thurs	16:15-17:30	1.25	Updated Endings work log from my own records.			Reviewed email updates and tasks from MDH; researched authority name for PRIN2.xml and replied to MDH's email on the topic.
2017-03-17	Fri	12:40-13:40	1				Skype meeting with JT and JJ re: Pantzer/DH project.
2017-03-19	Sun	10:40-12:25	1.75				Began cleaning up in-text citations and references in Pantzer/DH paper.
2017-03-20	Mon	11:15-12:30	1.25				Finished cleaning up in-text citations and references in Pantzer/DH paper; formatted the paper layout and text according to Harvard style conventions.
2017-03-21	Tues	9:30-9:45 & 10:00-10:45	1	Updated Endings work log from my own records.			Continued copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-22	Wed	10:45-11:45	1				Reviewed emails about confusing references to PRIN2 in COCK5 as well as authority name for PRIN2; finished copy-editing and updating JW's guide for encoding citations to bring it in line with MoEML practices and MLA style guide ed. 8.
2017-03-23	Thurs	17:00-17:30 & 18:00-18:45	1.25				Copy-edited list of works cited in JW's guide for encoding citations; began to address issues with bad links between MAPS1.xml and BIBl.xml.
2017-03-24	Fri	10:55-11:55	1				Finished addressing issues with bad links between MAPS1.xml and BIBl.xml.
2017-03-26	Sun	9:45-10:30 & 11:40-12:55	2				Reviewed and sorted MoEML Asana tasks; began proof reading JT's encoding in SEVE1.xml.
2017-03-27	Mon	8:40-9:40	1	Updated Endings work log from my own records.			Continued proof reading JT's encoding in SEVE1.xml.
2017-03-28	Tues	9:30-10:45	1.25				Uploaded SEVE1.xml to eXist; tried to find open-access digital surrogate for image from SEVE1.xml (on Folger LUNA, Google, etc.)--unsuccessful; marked SEVE1.xml complete on Asana; reanamed JW's citation guides in my SVN workflow folder; emailed JJ and KT re: JW's citation guides, MAPS1.xml, and WALL2.xml.
2017-03-29	Wed	11:15-12:30	1.25				Added THOM9 to BIBL1.xml as per JJ's request; emailed KT re: progress on MAPS1.xml, WALL2.xml, and JW's citation guides; updated documentation on encoding foreign text in encoding_practices.xml.
2017-03-30	Thurs	16:15-17:30	1.25	Updated Endings work log from my own records.			Reviewed emails from JJ and Alan Farmer re: "sublocations" in MoEML; replied to JJ and JT about possible way to encode "sublocations."
2017-03-31	Fri	8:45-10:00	1.25	Uploaded Endings work log to GitHub.			Reviewed email from JT re: programming for "sublocations"; revised document structure (i.e., <div> nesting) in encode_persons.xml; added link to National Council on Archives's "Rules for the Construction of Personal Names" to encode_persons.xml.
2017-04-04	Wed	4:30-5:00	0.5				Wrote two emails to JJ re: (1) MoEML SSHRC funding and (2) Robert Crease's article on Bacon's London.
2017-04-13	Thurs	9:45-10:45	1	Reviewed emails from MDH and other Endings team members about Endings web apps.			Reviewed MoEML emails re Asana tasks from KT and JJ; began listing locations in Robert Crease's article on Bacon's London in spreadhseet.
2017-04-15	Sat	9:30-10:00	0.5				Continued listing locations in Robert Crease's article on Bacon's London in spreadhseet.
2017-04-16	Sun	14:45-16:00	1.25				Finished listing locations in Robert Crease's article on Bacon's London in spreadhseet; identified MoEML @xml:ids for locations in Robert Crease's article on Bacon's Lonodn.
2017-04-17	Mon	9:30-10:00 & 11:30-12:00	1	Updated Endings work log from my own records,and uploaded it to GitHub.			Identified which locations in Robert Crease's article are already mapped by MoEML and mapped by Google.
2017-04-18	Tues	9:30-10:30	1				Added Agas map coordinates for THAM2.xml.
2017-04-19	Wed	9:00-10:00	1				Added Agas map coordinates for YORK7.xml; began adding Agas map coordinates for WEST6.xml.
2017-04-20	Thurs	11:00-12:00	1	Updated Endings work log from my own records.			Continued adding Agas map coordinates for WEST6.xml.
2017-04-21	Fri	9:45-10:45	1				Wrote MDH re: HCMC wesbites being offline; researched Spur Alley in Harben and Stow; looked into Google map coordinates for locations in Robert Crease's articles.
2017-05-05	Fri	15:45-17:00	1.25				Used "draw a shape" feature to add Agas maps coordinates for WEST6.xml.
2017-05-07	Sun	10:30-11:45	1.25				Encoded Agas map coordinates in WEST6.xml; researched coordinates for Spur Alley.
2017-05-08	Mon	10:30-11:30	1				Created new SPUR2.xml location document; added Agas coordinates to SPUR12.xml; updated location documents in eXist; emailed MDH re: Agas coordinates not appearing on Agas map.
2017-05-09	Tues	11:00-11:30 & 12:00-12:30	1				Added SPUR2.xml to SVN (forgot to do this yesterday); began generating complete "Bacon's London" Agas map; began drawing complete "Bacon's London" Google map.
2017-05-10	Wed	10:45-11:45	1				Continued drawing "Bacon's London" Google map.
2017-05-11	Thurs	11:00-12:00	1				Continued drawing "Bacon's London" Google map.
2017-05-12	Fri	11:00-12:00	1				Wrote point-form "exit" report of unfinished tasks from previous contract; emailed KT and JJ re: new contract.
2017-05-14	Sun	9:05-11:35	2.5				Finished drawing "Bacon's London" Google map; generated "Bacon's London" Agas map; reviewed MDH's email re: new Jenkins build process; commited global change in PERS1.xml, replacing all hyphens with EM dashes in date ranges; began writing email to Dr. Crease re "Bacon's London."
2017-05-15	Mon	10:20-11:20	1	Updated Endings work log from my own records.			Finished writing email to Dr. Crease re "Bacon's London"; reviewed KT's email re May 25th team meeting; began writing boilerplate message for @source="mol:stow_1598" in PERS1.xml.
2017-05-16	Tues	10:20-11:20	1				Replied to Dr. Crease re access to "Bacon's London" Google map; looked into how @source=" @source="mol:stow_1598" is being used in PERS1.xml; wrote JT re: how shouold @source="mol:stow_1598" be used?
2017-05-17	Wed	9:20-10:20	1				Replied to Dr. Crease re credits for "Bacon's London" maps; finished writing boilerplate message for @source="mol:stow_1598" and sent it to JT.
2017-05-18	Thurs	9:05-10:05	1				Cleaned up Asana inbox; began copyediting encode_persons.xml; began writing notes in preparation for May team meeting.
2017-05-19	Fri	9:00-10:00	1				Continued cleaning up Asana inbox; looked up "databses" glossary term in documentation; added "additional information" to CURT2 about playhouse shape; began removing <bibl>s from BIBL1.xml.
2017-05-23	Tues	11:00-12:00	1				Finished removing <bibl>s from MAPS1.xml.
2017-05-24	Wed	10:30-11:30	1				Finished writing notes for May 2017 team meeting; sent agenda items to KT for May 2017 team meeting.
2017-05-25	Thurs	13:00-14:15	1.25				May 2017 team meeting.
2017-05-26	Fri	9:30-10:30; 18:00-18:30	1.5	Updated worklog from my own records.			Added KT's digitlal pedagogy symposium presentation to publications_presentations.xml; added JJ, JT, and TLG's "Million's of Words" presentation to publications_presentations.xml; skype meeting with JJ and KT re: Endings contract.
2017-05-29	Mon	10:30-11:30	1				Began compiling bibliography of sources about project history for JJ.
2017-05-30	Tues	10:00-11:00	1				Continued compiling bibliography of sources about project history for JJ.
2017-05-31	Wed	11:30-12:30	1				Continued compiling bibliography of sources about project history for JJ.
2017-06-01	Thurs	10:30-11:30	1	Updated worklog from my own records; prepared timesheet and submitted it to JJ; sent my CV to Jennifer Polack (to be added to the Endings project website).
2017-06-04	Sun	10:30-11:45	1.25				Continued compiling bibliography of sources about project history for JJ.
2017-06-05	Mon	10:00-11:00	1				Continued compiling bibliography of sources about project history for JJ.
2017-06-06	Tues	10:00-11:00	1				Finished compiling bibliography of sources about project history for JJ.
2017-06-08	Thurs	18:15-19:15	1	Updated worklog from my own records.			Looked for feedback page in MoEML document collection; emailed JJ re: MoEML feedback page; began repurposing feedback.xml.
2017-06-09	Fri	10:10-11:25	1.25				Finished repurposing feedback.xml; emailed JJ re: new feedback page.
2017-06-11	Sun	13:40-14:25	0.75				Looked for step-by-step documentation for encodaing a location document (found:encode_location_doc.xml); emailed JT re: encode_lcoation_doc.xml.
2017-06-13	Tues	13:00-14:15	1.25				Met with JJ and JT re: DH 17 paper (proof of concept, graphics, writing style, etc.).
2017-06-15	Thurs	15:45-17:00	1.25				Took pictures of pages related to Pantzer location O.2. in STC vol. 3; began making spreadsheet of stationers and books associated with Pantzer locatoin O.2.
2017-06-16	Fri	9:00-13:00	4	Began researching and writing a taxonomy of documentation for DH projects.			Finished making spreadsheet of stationers and books associated with Pantzer locatoin O.2.; met again with JJ and JT re: DH 17 paper (proof of concept, graphics, writing style, etc.).
2017-06-19	Mon	11:00-12:00	1	Updated worklog from my own records; prepared timesheet and submitted it to JJ.
2017-06-20	Tues	10:00-10:30	0.5	Prepared timesheet for May 1-15, 2017 pay period and sent it to JJ, explaining that I had failed to send it earlier.
2017-06-23	Fri	21:30-22:30	1	Updated worklog form my own records.			Replied to Asana tasks re: adding a <respStmt> for Brook Isherwood to Stow and bios for new members of the leadership board; revised encode_persons.xml per CD and MDH's suggestion; updated bio statements for new leadership board members.
2017-06-26	Mon	11:40-12:40	1	Updated worklog form my own records.			Updated SVN and commited unversioned changes from Friday (no internet access then); finished downlaoding journal articles and other research resources on documentation types and methods in DH; wrote KT re updating team.xml via Asana.
2017-06-27	Tues	11:10-12:10	1				Replied to email from MK re: mayoral shows with transcriptions versus without transcriptions; continued working on taxonomy of documentation types; did a bit more research into DH documentation.
2017-06-28	Wed	9:00-9:40 & 11:00-11:20	1	Updated worklog form my own records.			Began encoding STEE2.xml (PP contribution).
2017-06-29	Thurs	10:30-11:30	1				Continued encoding STEE2.xml (PP contribution); added Hanseatic League to ORGS1.xml.
2017-06-30	Fri	8:55-9:55	1				Continued encoding STEE2.xml (PP contribution); added new sources from STEE2.xml to BIBL1.xml.
2017-07-03	Mon	11:20-12:20	1				Continued encoding STEE2.xml (PP contribution).
2017-07-04	Tues	8:00-9:00	1				Continued encoding STEE2.xml (PP contribution).
2017-07-07	Fri	11:35-12:35	1	Updated worklog from my own records; prepared timesheet and submitted it to JJ.
2017-07-10	Mon	10:30-11:30	1				Continued encoding STEE2.xml (PP contribution).
2017-07-12	Wed	9:20-9:50	0.5				Continued encoding STEE2.xml (PP contribution).
2017-07-18	Tues	10:00-11:15	1.25	Updated worklog from my own records; prepared timesheet and submitted it to JJ.			Continued encoding STEE2.xml (PP contribution); replied to email from JT re: DH STC paper.
2017-07-19	Wed	11:15-13:00	1.75				Continued encoding STEE2.xml (PP contribution); added new db entries to PERS1.xml and BIBL1.xml from STEE2.xml.
2017-07-20	Thuras	10:30-11:30	1				Continued encoding STEE2.xml (PP contribution); added new db entries to PERS1.xml and from STEE2.xml.
2017-07-21	Fri	10:00-11:00	1				Added new db entries to PERS1.xml from STEE2.xml.
2017-07-22	Sat	10:20-12:20	2				Continued encoding STEE2.xml (PP contribution); added new db entries to PERS1.xml and BIBL1.xml from STEE2.xml.
2017-07-24	Mon	11:25-12:25	1				Continued encoding STEE2.xml (PP contribution); added new db entries to PERS1.xml and BIBL1.xml from STEE2.xml.
2017-07-25	Tues	12:00-13:00	1				Continued encoding STEE2.xml (PP contribution); added new db entries to PERS1.xml and BIBL1.xml from STEE2.xml.
2017-07-26	Wed	10:20-11:20	1	Updated worklog from my own records.			Continued encoding STEE2.xml; added RHEN1.xml to placeography.
2017-07-27	Thurs	14:30-15:30	1				Added ANON25 ("Copperplate map") to MAPS1.xml.
2017-07-28	Fri	17:30-18:30	1				Added ANON25 to BIBL1.xml; added new location HANS7.xml (Steelyard guildhall) to placeography; encoded links to ANON25 and HANS7.xml in STEE2.xml.
2017-08-30	Sun	20:30-21:30	1				Researched and downloaded images for STEE2.xml.
2017-08-31	Mon	10:07-11:07	1				Began encoding images in STEE2.xml.
2017-08-01	Tues	18:45-19:00	0.25				Phone conversation with JT & JJ re: STC/MoEML paper for DH 2017.
2017-08-03	Thurs	10:30-12:00	1.5	Uploaded Endings work log to GitHub; sent timsheet to JJ.			Continued encoding images in STEE2.xml.
2017-08-04	Fri	20:30-21:30	1				Continued encoding images in STEE2.xml.
2017-08-05	Sat	11:05-11:20; 20:40-21:25	1	Updated work log from my own records.			Continued encoding images in STEE2.xml.
2017-08-06	Sun	10:30-11:30 & 20:25-21:10	1.75				Continued encoding images in STEE2.xml; met with JT via Skype re: STC/DH paper.
2017-08-07	Mon	21:30-22:30	1				Began revising STC/DH paper.
2017-08-08	Tues	12:15-15:45 & 20:00-21:00	4				Continued revising STC/DH paper; began preparing slides for STC/DH presentation; met with JT over the phone re: STC/DH paper; created new document mayoral_shows_progress_chart.xml for JJ.
2017-08-09	Wed	9:00-10:30 & 14:00-14:30	2				Finished revising STC/DH paper; finished preparing slides for STC/DH presentation; rehearsed presentation with JT in Montreal.
2017-08-14	Mon	15:30-16:30	1	Updated work log from my own records; exchanged emails with JJ and KT re: missing pay.			Wrote email to JJ with update re: documentation taxonomy.
2017-08-31	Thurs	9:00-9:45 & 11:30-12:15	1.5				Updated project CV as requested by KT; replied to Robert Crease; wrote bibliography of documentation resources.

## Sheet2
2016-07-25	Sun	7:15-12:45 & 12:55-13:55	6.5				Began fact checking and copy-editing MAPS1.xml.
2016-06-30	Thurs	9:15-10:15, 10:45-12:00, 12:15-16:30, 17:20-18:20, 23:30-0:00	8		6.56		Continued writing documentation for researching people in encode_persons.xml; continued fact-checking and copy-editing MAPS1.xml.
2016-07-04	Mon	8:30-10:30 & 11:00-16:30	7.5				Continued fact-checking and copy-editing MAPS1.xml; met with JJ re: back logged emails and MAPS1.xml workflow; searched for and prepared images for BEAR1.xml; met with JJ and JT to set up MoEML role-based email accounts.
2016-07-21	Thurs	8:00-10:45 & 14:50-19:05	7				Continued vetting and copy-editing MAPS1.xml (again).
2016-07-23	Sat	8:00-11:00 & 12:00-13:00	4				Continued vetting and copy-editing MAPS1.xml.
2016-07-27	Wed	9:00-16:30	7.5				Met with JJ re: vision for team page; helped JJ write FB post re: 10,000th revision; added Shannon Kelley as first author in BEAR1,xml; updated worklog and submitted timesheet; continued proofing MAPS1.xml; helped JJ clean out the MoEML office.
2016-07-28	Thurs	9:00-10:30 & 11:00-14:00 & 14:30-16:45	7		Met with JT re: RG vs. RG1 in references.xml		Continued vetting and copy-editing MAPS1.xml; met with MDH re: issue with <supplied> tags with <notes> in <date>s.
2016-07-29	Fri	9:15-13:00 & 13:15-16:30	7		Met with JT re: his improvements to rendering in Graves project.		Continued vetting and copy-editing MAPS1.xml; met with JJ briefly about how to handle early print surrogates in MAPS1.xml.
2016-08-31	Sun	8:00-12:00	4				Continued vetting and copy-editing MAPS1.xml.
2016-08-02	Tues	8:45-14:45, 14:58-15:08, 15:30-15:40, 15:50-16:05, 16:40-17:20, & 17:35-17:50	7.5				Continued vetting and copy-editing MAPS1.xml; continued writing documentation for encoding personography entries for modern contributors.
2016-08-04	Wed	8:45-16:15	7.5				Continued vetting and copy-editing MAPS1.xml; met with KT re: consultant duties in the fall.
2016-08-04	Thurs	8:45-16:15	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-08	Fri	8:30-12:00 &12:30-16:30	7.5		Met with JT re: his improvements to JavaScript and CSS in Graves.		Continued vetting and copy-editing MAPS1.xml.
2016-08-10	Mon	8:45-4:15	7.5				Continued vetting and copy-editing MAPS1.xml; helped JJ move ISE and MoEML office into HCMC.
2016-08-10	Tues	9:00-16:00	7				Continued vetting and copy-editing MAPS1.xml.
2016-08-10	Wed	10:45-15:00 & 15:15-17:00	6				Continued vetting and copy-editing MAPS1.xml.
2016-08-11	Thurs	8:45-13:00 & 13:30-16:45	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-12	Fri	8:45-12:00 & 12:30-16:45	7.5				Prepared and submitted timesheets for Jul 16-31 and Aug 1-15; continued vetting and copy-editing MAPS1.xml.
2016-08-15	Mon	09:00-16:30	7.5				Continued vetting and copy-editing MAPS1.xml.
2016-08-16	Tues	8:30-16:30	8				Continued vetting and copy-editing MAPS1.xml.
2016-08-17	Wed	8:30-16:30	8				Continued vetting and copy-editing MAPS1.xml; copy-edited JJ's entry re: Mitacs in news.xml.
2016-08-18	Thurs	9:00-17:00	8				Finished vetting and copy-editing MAPS1.xml; met with JJ re: Mitacs image guidelines.
2016-08-19	Fri	8:30-16:30	8				Last few revisions to MAPS1.xml content; began working on XSLT for MAPS1.xml.
2016-08-22	Mon	8:45-16:45	8				Met with JJ re: questions about MAPS1.xml; continued working on XSLT for MAPS1,xml; met with JT re: questions about XSLT.
2016-08-23	Tues	8:30-16:30	8				Began going through Martin's list of unlinked binary documents; continued working on XSLT for MAPS1.xml; met with JJ re: questions about MAPS1.xml; met with JJ and JT re: what we can do with data from DEEP.
2016-08-24	Wed	8:45-13:30, 13:45-15:10, & 16:20-17:15	6.75				Continued working on XSLT for MAPS1.xml database.
2016-08-25	Thurs	8:45-2:00, 2:55-3:05,3:20-3:45, & 4:00-6:10	8		Met with JT re: CSS design for Graves website.		Continued working on XSLT for MAPS1.xml database.
2016-08-26	Fri	8:00-12:45	4.75				Continued working on XSLT for MAPS1.xml database; worked on Millions of Words abstract with JJ; began adding maps from Strype to MAPS1.xml database.
2016-08-29	Mon	8:15-16:45	8.5	Attended Ending meeting.			Continued adding maps from Strype to MAPS1.xml database; worked on Millions of Words with JT.
2016-08-30	Tues	8:30-13:30 & 13:45-16:45	8				Finished adding maps from Strype to MAPS1.xml database.
2016-09-12	Mon	9:00-4:30	7.5				Designed template for MAPS1.xml database; continued working on XSLT for MAPS1.xml database.
2016-09-16	Fri	8:00-10:45	2.75				Continued working on XSLT for MAPS1.xml database.
2016-09-17	Sat	10:00-12:30	2.5				Added KAET1 to team.xml; edited KAET1 entry in PERS1.xml; changed photo for LAND2 in team.xml.
2016-09-19	Mon	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-20	Tues	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-21	Wed	7:30-9:00	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-22	Thurs	8:15-9:00	0.75				Continued working on XSLT for MAPS1.xml database.
2016-09-23	Fri	8:30-9:00	0.5				Continued working on XSLT for MAPS1.xml database.
2016-09-28	Wed	8:00-9:30	1.5				Continued working on XSLT for MAPS1.xml database.
2016-09-29	Thurs	8:00-9:00	1				Submited timesheet to MDH; continued working on XSLT for MAPS1.xml database.
2016-09-30	Fri	8:30-10:00	1.5				Updated Endings worklog; continued working on XSLT for MAPS1.xml database.
2016-10-04	Tues	13:30-14:30	1				Continued working on XSLT for MAPS1.xml database.
2016-10-08	Sat	16:00-19:00	3				Continued working on XSLT for MAPS1.xml database.
2016-10-12	Wed	8:00-9:00 & 16:00-18:30	3.5				Continued working on XSLT for MAPS1.xml database.
2016-10-13	Thurs	10:00-12:00	2				Manually edited XML in MAPS1.xml; continued working on XSLT for MAPS1.xml database.
2016-10-14	Fri	12:00-14:30	2.5				Continued working on XSLT for MAPS1.xml database.
2016-10-15	Sat	10:00-12:00 & 14:00-15:00	3				Continued working on XSLT for MAPS1.xml database.
2016-10-17	Tues	8:00-8:30`	0.5				Continued working on XSLT for MAPS1.xml database; updated Endings worklog.
2016-10-21	Fri	10:30-11:00 & 17:00-18:00	1.5				Continued working on XSLT for MAPS1.xml database; emailed JJ, KT, and JT re: progress on MAPS1.xml database and follow-up to LBTD stationers.
2016-10-22	Sat	9:30-11:00 & 17:00-17:30	2				Met with JT re: issue in MAPS1.xml XSLT.
2016-10-24	Mon	8:10-9:10	1				Continued working on XSLT for MAPS1.xml database.
2016-10-31	Mon	`13:30-14:30	1				Updated Endings worklog; continued working on XSLT for MAPS1.xml database.
2016-11-01	Tues	13:30-14:00	0.5				Continued working on XSLT for MAPS1.xml database.
2016-11-02	Wed	10:00-11:00	1				Continued working on XSLT for MAPS1.xml database.
2016-11-03	Thurs	14:00-15:30	1.5				Made final few changes to XSLT for MAPS1.xml database; emailed JT to schedule phone meeting re: XSLT; reviewed MoEML emails; added new MoEML blog posts to media.xml.
2016-11-04	Fri	15:00-16:30	1.5				Prepared MAPS1 XSLT for JT to review; emailed JT with troubleshooting questions re: MAPS1 XSLT; updated media.xml on eXist; emailed MoEML team re: changes in media.xml.
2016-11-06	Sun	9:00-10:00	1				Began identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-07	Mon	8:30-9:30	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-08	Tues	12:00-13:00	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-09	Wed	8:15-9:15	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-10	Thurs	8:15-9:30	1.25				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-11	Fri	9:00-9:30 & 10:30-11:15	1.25				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-12	Sat	11:00-12:00	1				Uploaded PERS1.xml and team.xml to eXist on JJ's behalf;Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-13	Sun	10:00-11:00	1				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-14	Mon	8:55-9:25 & 11:00-11:30	1	Updated Endings work log from my own records.			Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-15	Tues	12:30-13:30	1				Added new locations from MAPS1.xml to placeogrpahy; emailed MDH re: issues with schematron in oXygen.
2016-11-16	Wed	9:00-9:45	0.75				Continued identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy.
2016-11-18	Fri	10:00-11:00	1				Finished identifying/tagging locations mentioned in MAPS1.xml; added new locations from MAPS1.xml to placeogrpahy; began looking into ways to clean up extra spaces and character in output of MAPS1_output.xsl.
2016-11-20	Sun	9:00-10:30	1.5				Reviewed JT's email about how to improve MAPS1_output.xsl and experimented with his suggestions; I decided that it would be quicker to clean up the output of MAPS1_output.xsl manually.
2016-11-21	Mon	11:15-12:15	1				Cleaned up the output of MAPS1_output.xsl manually; began copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-22	Tues	12:15-13:15	1	Updated Endings work log from my own records.			Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-23	Wed	9:00-10:00	1				Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-24	Thurs	9:30-10:30	1				Continued copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates.
2016-11-25	Fri	8:30-9:30	1				Finished copying bibl entries for maps from MAPS1.xml into BIBL1.xml and removing duplicates; renamed MAPS1.xml as MAPS1.xml_ and took it off eXist (in order to address duplicate IDs errors); uploaded BIBL1.xml to eXist.
2016-11-26	Sat	9:30-10:30	1				Renamed MAPS1_db.xml as MAPS1.xml; began formatting MAPS1.database before uplaoding it to eXist.
2016-11-27	Sun	9:30-11:00	1.5				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-11-28	Mon	9:00-10:00	1				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-11-29	Tues	8:30-9:30	1	Updated Endings work log from my own records.			Continued formatting MAPS1.database before uplaoding it to eXist; reviewed and responded to email re: MAPS1.xml from JT.
2016-12-01	Thurs	9:00-10:00	1				Continued formatting MAPS1.database before uplaoding it to eXist.
2016-12-02	Fri	10:30-13:00	2.5				Finished formatting MAPS1 database; began adding cartographers to PERS1.xml from MAPS1.xml.
2016-12-05	Mon	10:35:11:35	1				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-06	Tues	11:00-11:45	0.75				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-07	Wed	10:00-11:00	1				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-08	Thurs	10:45-11:00	0.75				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-09	Fri	11:00-11:30	0.5				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-16	Fri	9:45-11:00	1.25				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-18	Sun	10:30-11:00	0.5				Continued adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates).
2016-12-19	Mon	13:00-14:30	1.5				Finished adding cartographers to PERS1.xml from MAPS1.xml (assigning unique @xml:ids and removing duplicates); removed non early modern cartographers from PERS1.xml.
2016-12-20	Tues	8:00-10:00, 13:00-16:30, & 18:30-21:00	8				Began testing external links in MAPS1.xml and correcting them as needed; worked through diagnostics errors for MAPS1.xml, making MAPS1.xml ready for publication.
2016-12-21	Wed	7:30-9:15 & 15:20-16:50	3.25				Finished testing external links in MAPS1.xml and correcting them as needed.
2016-12-22	Thurs	8:30-9:15 & 10:30-10:45	1				Wrote and sent email to MoEML team about next steps for MAPS1.xml.
2017-01-03	Tues	10:00-11:15 & 22:15-22:45	1.75				Began alphabetizing MAPS1.xml; began writing email to BT about his role in copy editing MAPS1.xml.
2017-01-04	Wed	9:30-10:15, 16:35-17:20, & 18:00-18:30	2				Finished alphabetizing MAPS1.xml; continued writing email to BT about his role in copy editing MAPS1.xml; continued encoding Roland's WALL2.xml.
2017-01-05	Thurs	9:00-9:30 & 17:30-18:00	1				Finished writing email to BT about his role in copy editing MAPS1.xml; continued encoding Roland's WALL2.xml.
2017-02-31	Tues	9:30-11:30	2	Updated Endings work log from my own records.			Finished stylizing graphics in WALL2.xml (adjusting margins to fit on page); began reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-01	Wed	11:30-12:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-03	Fri	10:35-11:35	1	Tabulated hours worked as against alloted hours in my contract.			Tried to add Leah Thomas's article to Project CV (it's already there); continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-04	Sat	9:00-10:30	1.5				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-06	Mon	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-07	Tues	8:00-9:00	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-08	Wed	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-09	Thurs	16:20-17:20	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-10	Fri	9:30-10:30	1				Continued reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database. Identified missing entriesand corrected publication years in MAPS1.xml.
2017-02-11	Sat	10:00-12:30	2.5				Added Catriona Duncan's two presentations and one blog post to project CV; began writing email to JJ and KT re: progress on MAPS1.xml and WALL2.xml.
2017-02-13	Mon	10:30-11:30	1				Finished writing email to JJ and KT re: progress on MAPS1.xml and WALL2.xml; finished reordering index of maps (the first <div>) in MAPS1.xml to reflect the order of maps in the database.
2017-02-15	Wed	10:45-12:00	1.25	Finished updating my Endings work log from my own records.			Standardized spelling of "bird's-eye" in MAPS1.xml. Organized and cleaned-up Asana tasks.
			329.75
			8.793333333