## Sheet1
Date	Day of Week	Time	Hours Logged	Endings	Graves	Mariage	MoEML	Moses
05/16/2016	Monday	11:00-4:45 & 8:00-10:00	7.75	Working on presentation on diagnostics for Endings			Writing individual page diagnostics, which runs as a transformation in XSLT. It allows for a quick way for encoders to check their work instantly. I think it should be added as a validation step in the process.
05/17/2016	Tuesday	10:30-4:30 & 5:30-6:30	7	Endings “Study Day.”			Worked on controller for diagnostics and next free id processing.
05/18/2016	Wednesday	11:30-4:30 & 6:00-7:00	5	Checked out various repos and wrote a build process for splitting out timesheets into various projects.			Working on controlling for next free id and diagnostics. Working on the modularization of diagnostics.
05/19/16	Thursday	10:30-4:30 & 6:00-8:00	8		Discussed future goals/outcomes with MH for Graves. Wrote up a timeline for continuing onwards.		Working on modularizing diagnostics a bit more; from 6-8, working on a check for images, which turned out to be more complicated than I thought. There are many images that are not in svn but are in eXist and vice versa. There are almost a number of images that are in different directories between the two systems. Should be fixed soon, even though we're going to be moving over to eXist packages in the near future anyways.
05/20/2016	Friday	12:00-5:00	5		Working on diagnostics for graves project. Rewrote the broken references template so that it groups them by document and then by date. I thought it might be a bit more RA friendly.		Discussing Stow with JJ/MH/KT and working on stow proofing (reminder: one half ward = 3h between two people; so 12 labour hours per ward for proofing reading).
05/24/2016	Tuesday	10:00-4:30	6.5				Working on some diagnostics work and then working on historical people for MoEML's stow PERS-athon. Writing code to generate a stats page.
05/25/2016	Wednesday	2:30-4:45 & 7:30-9:30	4.25		Working on diagnostics for graves project. Fixing minor issues in the wrong references as well as some stylistic things; I've decided to do the red/green colour coding like MoEML. I also started working on a wrong ref/type check. Finished up wrong ref/type check and doing some other ad hoc checks across the data, so that I can start compiling what kind of rules might be necessary for the schematron.
05/26/16	Thursday	10:30-4:30	5		Working on diagnostics output; writing some queries about some entities in the data (orgs vs names etc).		Working on diagnostics and migrating the new diagnostics stuff over to the regular build. That now seems to be working, so started checking diagnostics. Realized I need to make my duplicate pers checker a bit more nuanced somehow, since I've been finding multiple duplicate people.
05/28/2016	Saturday	2:00-7:30	5.5				Working on diagnostics and creation of statistics page for the site. Working on proofing people as well.
05/29/2016	Sunday	5:00-8:30	3.5				Working on tagging dates in Stow. Should be closed to finished now. Also doing some reading for the dates paper, and writing team meeting topics.
05/30/2016	Monday	10:30-7:30 (-lunch)	8				Fixing a bug in the person diagnostics, which ended up shoring up some more issues with the person diagnostics. Also worked on generating a stats page for the site in the process of the static build. Working on proofing people for Stow. Nearly finished! Working on getting locations ready to be proofed also.
05/31/2016	Tuesday	8:30-4:30	8

06/01/2016	Wednesday	10:30-4:45	6.25				Made good progress on static build; styling issues are getting a bit better, graphics are working, gloss and orgs AJAX frags are now being produced in a better way.
06/02/16	Thursday	1:00-5:00	4				Team meeting and wrap-up.
06/03/16	Friday	4:00-11:00	7				Majorly playing catch-up due to illness/appts over the last few days. Made mighty progress with statistics.xml.
06/04/16	Saturday	11:30-3:30	4				Finishing up some work on stats, adding a new script to the diagnostics stuff, wrote some new diagnostics, fixed sourceDescs in many files and wrote some schematron to ensure tables have the right number of cols/rows.
06/06/2016	Monday	10:00-11:00 & 1:30-4:45	4.25				Working on static build process; met with TL to discuss dates essay; running link checker on site (should be completed by midnight, perhaps)
06/07/2016	Tuesday	10-4:30	6.5				Working on stow metadata with JJ. Began working on TEI header and got through respStmts. Decided to implement new system of more granular resp on text elements. Working on linkchecking processes with MH, then more Stow metadata.
06/08/2016	Wednesday	11:00-5:00	6				Working on finishing respStmts and some more stow metadata with JJ. Disambiguating about PARI location. Helped TL with creating GLOSS1 stuff.
06/09/2016	Thursday	11:00-5:00	6				Working from home due to illness. Working on diagnostics, compiling list of PPP for KT, Xpath for ISE plays.
06/10/2016	Friday	10:00-3:00	5				Working on Stow metadata some more, and attempting to figure out best way to do responsibility in regards to the stow fragments. Working more on linkchecking document stuff for MoEML. Working on stow responsiblity fragmenents, and writing an XSLT that processes the Stow progress chart and creates <respStmt>s for each person.
06/13/2016	Monday	11-5:00 & 7:00-8:00	7		Working on Xpaths with TL and showing him FLWOR statements for work on Graves diagnostics.	Working on linkchecking for Mariage and writing new, better diagnostics. At home: checking URLs in Mariage and trying to figure out why these things don't work!	Discussing the static build with MH.
06/14/2016	Tuesday	12:30-4:00	3.5	While this was discovered working with MoEML, it applies too basically all of the Endings projects: there has been a breakthrough to the schematron ANT warning message. You can add an @debugMode='true' to the schematron task, which produces a debug.xslt file. What seems to happen is that the skeleton XSLT that is produced creates an xsl:apply-templates select=”*” indiscriminately, which is nonsensical for @* or text(). I spent a bit of time poking around the source code and the various compilers to see if I could fix it, but no luck (my comments wouldn't even display in the debug file). We could file a bug, but I'm unsure as to whether or not anything would come of it. Next task, though, is to look at the oXygen spec and see if there's any info on how they use the compilers.		Working on Mariage diagnostics and discussing URI escaping with MH. Trying to figure out why linkchecker insists on escaping rightly escaped URIs.		Chatted with Sarah briefly about future diagnostics checks, which she will compile and send to me at a later date.
06/15/2016	Wednesday	10:00-3:00 (tentatively)	5
			64.5
06/17/2016	Friday	10:00-11:00	1	Catching up on emails for all projects.
06/18/2016	Saturday	2:00-5:00	3				Creating an XSLT that processes all of the XSLT files and the Ant build to create programmer documentation. It's not perfect, but I think it's a great start for our project. Did some research on oXygen's baked in documentation creation, but I'm not the biggest fan. I think it's good as inspiration, though. Our own should be a bit better and also be formatted into TEI so that it works for other projects.
06/19/2016	Sunday	3:00-4:30	1.5				Fixing up DEEP numbers in the data. Wrote an XSLT for it, but realized it was probably safer to do by hand.
06/20/2016	Monday	10:30-4:30	6				Working on fixing up more DEEP numbers primarily. Fixing up some bad links in diagnostics (I think that they should break the build. They pile up very easily and feasibly break the site if any exist). Working on static build maintenance and realized that the validation task in ANT is doing everything we want it to do; oXygen must have their own compiler that checks to see if the rule matches an @* or text() and then uses <xsl:apply-templates/> iff it makes sense. The one used by ANT does not, thus producing what were once thought of as pesky warnings. But, we're realizing that it's allowing invalidities to slip through the cracks. My job tomorrow is to go through and rewrite the schematron rules so that they don't produce warnings, if possible.
06/21/2016	Tuesday	10:00-12:00	3			Working on fixing schematron rules to get rid of the warnings in the schematron.	Working on fixing schematron rules to get rid of the warnings in the schematron.
06/25/2016	Saturday	3:00-4:30	1.5				Working on PERS1 diagnostics and fixing up some schematron rules for capitals and notes, as well as Roman numerals.
06/28/2016	Tuesday	11:00-4:30 & 5:30-8	8				Working on diagnostics creation; Stow meeting; working on renditions in the header and beginning the major work of Stow documentation, etc.
06/29/2016	Wednesday	8:30-4:30	8				Working mostly on the static build documentation; getting the code written for that and fixing some documentation. It's looking quite good, and might be a good thing for the other projects too—we just use the same-ish code to make TEI documents. Those TEI documents are styled however that project wants. Spent some time fixing bugs in other static related things. Also combed through the many Asana tasks that I was assigned; most could be reassigned, but I'll have to take a longer look.
06/30/2016	Thursday	8:30-4:30	8
			40
07/01/2016	Friday	STAT	STAT
07/02/2016	Saturday	11:00-1:00	2				Adding Brooke Isherwood to the DB, editing her personography entry, modifying stow diagnostics code, adding to the stow progress chart.
07/04/2016	Monday	10:00-4:30	6.5				Writing location pages and working on Stow and PERS metadata with JJ.
07/05/2016	Tuesday	11:00-4:30 & 5:30-8:00	7				Chatting with MH re: on Stow diagnostics; Locathon abstract writing and fixing up some schematron rules.
07/06/2016	Wednesday	11:00-4:30 & 5:30-8	7		Discussed graves with MH and started working on normalizing some aspects of the site. Working on changing the div structure of enclosures and fixing numerous errors along the way.
07/07/2016	Thursday	10:00-4:30	6.5		Working more and more on the XSLT that normalizes dates, datelines, and other aspects of the data. Adding some tei elements to the RNG, adding prefix defs, etc. Ran XSLT on all abstracts and entries and then fixing a few @xml:ids and other things by hand. Also wrote an applet for Firefox that brings me directly to a page image or the diary page from the W3C date entered in the browser.
07/08/2016	Friday	10-4:30	6.5		Working on the graves site map and standalone code. We're at the point now where we can start making XHTML pages.		Adding a schematron rule for broken local links and trying to fix it throughout the source data and the static build. Shoring up a bunch of errors in our development code, which is helpful, but many are difficult to figure out. Also attempting to fix the Next Free Id code so that it works on windows. Difficult fix, still not done.
07/12/2016	Tuesday	11:00-5:00 & 7:00-9	8		Writing some notes and getting some prelimary stuff sorted out for Graves. Would love to get all of the pages being made with all of the appropriate elements by the end of next week.		Proofing, editing, adding, and moving articles from proofing to published; discussing Stow rendering with MH; added schematron rule for empty change elements; modifying the stow chapter module to handle @resp that point to local respStmts. Edited and added respStmts to the header of stow_1598 and put the appropriate
13	Wednesday	11:00-5:00 & 7:00-9	8		Started working on the outline for XHTML page processing. Noticed that there's a weird '../blank' for some of the @facs which came from the index. I've made them invalid so the build will persistently break until I've fixed them. Also noticed a few more references that are broken. Fixed as many as I could, but there's still one that I can't figure out. I'll have to wait for TL or EGW. So, the standalone XMLs are broken at the moment, too.		Working a bit on Stow, helping CD with some SVN issues, writing a couple simple schematron rules, writing and editing a few location articles.
14	Thursday	9:00-5:00	8		More progress on the graves build; think I have a plan of attack for the future. Site map page and xml markup pages are now coming out alright, next will be the regular pages, which will be a lot more work.		Meeting with JJ and MH regarding Stow; figuring out that we won't need review packages, but just a splash page on the site. Rewrote Stow splitting code so that it works a bit better and is a bit cleaner and also comes before the flattening stage. Created a peer-review page that has a generated div of things needed to be reviewed. Worked with JJ on re-organizing stow_1598 so for the TOC.
15	Friday	11:00-4:30 & 5:30-8	8		Working on graves build. Refactored it completely so that it works as a template going off of the site_map. I changed the sitemap so that it only listed each page once, and now includes an @corresp that points to the XML file (and, if pertinent, div) that the page should be built from and the facsimiles that it will need to include. The building process is now a template that matches the <ref> in site_map in a particular mode. All pages are building successfully and content is at least being brought over.		Chatting with JJ and MH on document categories etc. Reminder: change the directory for “classes” to “teaching” at the request of JJ.
			67.5
07/18/2016	Monday	10:30-4:30	6		Getting the calendar module up and running. I've got the calendar creating properly (with a sort of clunky recursive function) and the various views being sorted out. I just realized that the calendar links are context dependent, which will be something I have to account for tomorrow. Once this is up and running, all I have left to do for the regular page structure is the facsimile and other bits sideview. Once that's all finished, though, then its display and styling. I'll try and get everything at least wrapper-wise done by possibly Thursday. I'd like to get a site where everything is in the right place by next week so that TL and EGW can start to fix any errors that might be getting in the way of display. Also added @n attributes to diary entries that needed them.		Chatted with MHM with the selector attribute on rendition. He discovered that in XSLT 2.0, you can't match using descendant or ancestor axes; however, we will work on the assumption that we're applying templates to the text and then applying templates oinly with parental inheritance (ie note > p) or anything in text. For example, selector=”p” will select text/descendant::p by default of matching text and applhing templates; but note >p will produce an XSLT that says match=”note/p”, which won't cause an ambigious rule since more specific templates get higher priority. This should be a nice way to work around some issues.
07/19/2016	Tuesday	12:00-5:00	5		Getting Graves rendering up and running. Main doc, sidebar, and footer all almost running. Have to figure out small issues with the navbar since there are so many distinct issues, but other than that the body is looking pretty decent.		Reverting some location documents, helping CD with new rendition rendering and talking about XTREME stow rendering w MH.
07/20/2016	Wednesday	2:00-5:30	3.5		Doctor's apt in the afternoon, but spent the rest of the day working on rendering of the calendar and other CSS fixes.
07/21/2016	Thursday	12:00-5:00	5		Working on more CSS, changing the font sizes rules from absolute values to ems (at the suggestion of PS). Importing of editorial notes and other appendix content is going well. Project for tomorrow is determining the two different views for the onload event of the index page. Then I'll start working on other importing issues.
07/22/2016	Friday	12:00-5:00	5		Fixing XHTML5 templates, adding more for ins, dels, etc, and cleaning up some source code. Rewrote the standalone module a bit so that it pulls in everything—have to think about AJAX calls and whether that will ever be needed (I don't think so).
07/23/2016	Saturday	2:00-4:00	2		Working on JS for index page; working alright, but styling is difficult.
07/25/2016	Monday	12:00-5:00 & 6:30-8:30	7		Working on index page and sitemap for Graves. Getting abstracts and entries a bit more reliably fixed.
07/26/2016	Tuesday	11:30-5:00 & 6:30-7:00	6		Chatting with PS re: styling and “flex”; that might be the best option for rethinking how we want the site to go. Working a lot on the appendix and CSS fixes.		Met with JJ and MH to discuss Stow rendering, particularly surroudning the various views. Helping CD with commit issues.
07/27/2016	Wednesday	12:00-5:00	5		Implemented flex design and had to rearchitect the <div> structure, but now its working well. Widths are far nicer and eveyrhing is looking better. Wrote hte JS to make references work and hide the appendix content. Just need to get the positioning of the pop-ups		Chatting with JJ, MH, and TL about the feasibility of putting photos in PERS1. Talking about date code
07/28/2016	Thursday	11-7	8		Working from home on Javascript and other graves work; struggled with getting bibls to work properly, but it turns out I just want them to be different in general. Instead of trying to format them into a correct bibl with puncutation and line breaks (which is difficult to do in a basically biblStruct structure), I decided to just make it a list with horizontal headings that give the local-name of the element. I think it's a nicer, cleaner way of display bibliographic citations, and it looks a lot like the way we display handNotes anyways (which still need to be added into the build).
07/29/2016	Friday	12:00-5:00	8		Working more and more on the CSS for Graves; rewriting some of the older generation code so that I can get the other pages to flex properly. Small fixes to the CSS that inevitably are proliferating. Trying to get the iFrame stuff to work, but I'm not sure if we possible can. MH gave a good suggestion: without JavaScript, use an a href with some custom attributes that has a link to just graphic and an iframe wherein the graphic loads; with JS, either load in the iframe for that graphic's page and alter the page itself (which is allowed since it's not cross domain) or reconstruct the div on the side using the custom attributes (possibly the best way to go since most of the data is already getting added to the document).
07/30/2016	Saturday		8				Received plague document from Kate Casebeer; restructured into list format and added teiHeader and information. Got it validating and added style throughout. There are a few toponyms left untagged that KC queried, but other than that the document is well-encoded. After a few rounds of proofing and a bit more encoding, it should be out the door.
07/31/2016	Sunday		8		Working on getting hand stuff built for Graves, which is confusing...no real clue where this data is coming from. Also trying to get silly iFrame thing working but nothing seems to want to style properly.		Working further on the plague document and reformatting into tabular structure; attempting to research Parishes but to little avail.
08/01/2016	Monday		STAT
08/02/2016	Tuesday		1				Pulled away from work for personal reasons; answering emails and queries.
08/03/2016	Wednesday	11-5:00	6		Almost completely rewrote calendars.xsl so that the gallery calendar and the individual page calendars are completely forked; structurally the two are quite similar, so a lot of the existing code could be parameterized so that the functions work for both, but there are significant enough differens so that they are separate things. I decided to use templates with modes to handle the two, which I think works very nicely.		Working on plague documents still, tabular format broken so I had to re-do and getting editorialDecl looking nicer. Chatting with TL re: @facs attribute and proper attribution. Folger's fails to give a good URL for its images, so just pointing to the image (or using a private URI) seems unfeasible; the Folger record be correct to point to using the @facs attribute? Is it truthful to do so....the TEI guidelines say that @facs can point to items with metadata associated, which is what Folgers is doing. The other option would be to download the @facs, which JJ suggested the other day; this is a good idea in one sense, because we can use this solution when we're displaying the stow facsimile pages for 1633 or when the Uvic library gets their own 1598. But it is also problematic for attributing our sources correctly (pb does not allow an @source). We'll have to think about this more carefully.
08/04/2016	Thursday
08/05/2016	Friday

	Start of New Contract
09/12/2016	Monday	10:30-4:30	6	Working on MoEML diagnostics for Diagnostics paper; chatting with MH about the paper and what needs to be done			Meeting with JJ and TL regarding Million Words project.
09/15/2016	Thursday	10:00-4:00	6	Working on MoEML diagnostics; parameterizing the checks and finishing up ANT build and tasks.
09/20/2016	Tuesday	3:00-7:00	4	Working on C3 generation for the MoEML diagnostics.
09/22/2016	Thursday	10:00-4:00	6	Hammering out bugs in the diagnostics report; researching for the paper
09/25/2016	Sunday	9:00-12	3	Working on C3/D3 charts and fixing up display; figuring out best practices for displaying the charts and getting all of that working.
10/09/2016	Sunday	12:00-2:00	2	Reading and research for the diagnostics paper
10/14/2016	Friday	1:00-4:30	3.5	Chatting with MH re: diagnostics paper; started working on an XSLT that grabs the SVGs from the generated XML rendering of the diagnostics page. Sort of working, but there's a bit of work left to do on it (y-axis isn't rendering properly.)			Working with JJ on the Million Words paper; catching up on MoEML and volunteers.
10/15/2016	Saturday	1:00-2:00	1	Reading Reed paper and baliage conference for the diagnostics paper			Slight fixes to PERS1.
2016-10-17	Monday	10:00-4:00	6	Working on diagnostics paper with MH; Endings meeting.			Million words project; discussing with JJ and TL; started writing a build process that takes JJ's pantzer spreadsheet and converts it to a tagged TEI table (a one-off build).
2016-10-18	Tuesday	4:00-7:00 & 9:30-11	4.5	Reading MH's diagnostics intro and sending off questions re: definitions.			Worked on and finished million words build; hand-fixed some errors in the process. Now, TL and JJ have to add locations. Once that's done, I can write/run XSLT that correlates the Pantzer locations with MoEML locations and create a speadsheet. We can make that into an XML document, but we'll have to see what the best output is. At 9:30: decided to go ahead and create the XSLT for the Pantzer correlation. It was simple to do and it works well. Wrote it in both TEI and XHTML5 (for email/display purposes), but will certainly do it in TEI first. Have to think about whether we should create KMLs/JSONs.
2016-10-22	Saturday	7:00-1:00	6	Working on diagnostics paper			Meeting with TL regarding Millions of Words.	Ported over the MoEML diagnostics report building process over to Moses. Got that working well.
2016-10-23	Sunday	9:00-10:00 & 1:00 -3:00	3	Working on diagnostics paper.				Working on modifying graphs so that the number of entries are also present; emailing Ewa, Sarah, and Martin about progress.
2016-10-26	Wednesday	10:00-11:00	1	Working on diagnostics paper.
2015-10-28	Friday	3:30 – 6:30	3	Slight edits on diagnostics paper before MH sends it off.			Creating a build process for adding DEEP numbers to a local copy of the MoEML site.The original plan was to rebuild the static site (using quick or something like that), then copy it all into the million_words dir, and then add DEEP numbers where necessary. Not going to work, though: The static build process fails because of a lack in available memory; after multiple attempts to fix it, I can't (which may prove problematic in the future), so I've had to resort to an awfully hacky sort of way of doing this: copying over the necessary ancillary files and then getting the necessary .htm files from the Jenkins server. So, this site is not very functional, but it least works for screenshots and proof of concepts.
2015-10-30	Sunday	4:00-5:00	1				Researching for Million of Words paper and attempting to get some writing down; sending off some briefing notes for a meeting tomorrow w/ JJ and TL.
2015-10-31	Monday	1:15-2:30 & 4:00-5:30	2.75				Mtg with JJ and TL, working on Million Words/DH paper. Down to the wire.

2015-11-01	Tuesday	12:00-2:00	2				Working on Million words presentation and finishing up some work in creating the screenshots.
2015-11-02	Wednesday	8:00-11:00	3				More work on million words presentation...
2015-11-03	Thursday	11:30-12:00 & 3:00-4:00	1.5				Presenting million of words and working on it some more.
2015-11-06	Sunday	11:00-12:00	1				Working with TL on MAPS1.
2015-11-08	Tuesday	7:00-9:30	2.5	Trying to figure out why no build processes are working on my computer. Even the next free id is saying there isn't enough heap memory space. Tried doing ANT_OPTS=-Xmx1024m but nothing works. Really frustrating.			Thinking about modifying nextFreeId.xml to accept multiple arguments. Would have been fairly straightforward if the build processes were working on my laptop.

2015-12-06	Tuesday	3:00-4:30	1.5				Getting back into the swing of things. Working through some diagnostics stuff and PERS1 is still full of broken IDs that I'm positive CD fixed. I'm going to email and see what might be up with that. Also fixed the 404s in BIBL1. Figured out what was wrong my ANT_OPTs: I had stored a couple copies of the data locally (in my working_files and in utilities) for various projects and stuff. So, I had the repo almost 4 times over, which of course could not be stored in memory. Builds are working now.
2015-12-08	Thursday	3:00-5:00	2				Working through some more 404s, and added a diagnostic check (long overdue) for div[@rend='hidden']. 4 instances of that right now, most of which in PPP documents. Will forward onto KT/JJ for evaluation.
2015-12-10	Saturday	5:00-6:00	1				Working on some more diagnostics stuff, and adding some names to ORGS1.
			4.5
2016-12-22	Thursday	12:00-1:00	1	Reading and responding (to MH) re: DH review.			Reading and responding to DH review stuff with JJ and TL.

2017-01-16	Monday	1:00-3:00	2				Working on diagnostics, mostly 404s, bibls, and name refs.
2017-01-23	Monday	9:30-11:45	2.25				Working through the abstracts I wrote a while ago that TLG recently edited; encoded these documents, added GIS coordinates and abstracts, added respStmts, and set to publish. Double checked that the documents were good using the individual diagnostics, which I had forgotten about—they work quite well! It would be great to integrate them a bit more into the process, but I'm unsure how we might go about that. Also tried running the static build again, but running into similar overflow memory errors. Finally emailed MH about it. It might just be my machine and it might not be a concern (since we expect people who are running the build to be using fairly good equipment), but I know that we've talked about how one of the benefits of the static build is its portability and usability for conference settings. This error might challenge that.
2017-01-26	Thursday	3:00-4:00	1				Quickly popping in to chat with MH/JJ about the STC project. Had to go on a hunt for it.
2017-01-27	Friday	10:30-1:30	3	Endings mtg. Mostly a review of abstracts and an introduction to the communications RA / the communications plan.			Mtg with JJ and MH re: DH project.
2017-01-30	Monday	2:30-4:45 & 5:30-7	3.75				Scanned one page of the STC to test the output. Had some hiccups with technology, but the page turned out quite nicely. At home, started to play around with Tesseract to see if it's a good alternative to Abbyy (especially since it's open-source, open-code). Needed to play around with it a bit more, so I decided to try OCRing the Sugden. I realized I needed a whole suite of tools (pdfunite, etc) and I would have to write some sort of script, which I am not too familiar with.	Working on diagnostics with SK; mostly just getting the diagnostics stuff understood and making a plan for implementation over the next few days.
2017-01-31	Tuesday	2:00-4:15	2.25				Working on the ocrPDF script, which will be a very handy tool in the future. OCR'd Sugden and played around with the results a bit; they look decent, but not great. I then experimented with different density settings/monochrome etc but I think the best way to go about is a density of 300, since the difference from 300 to 1000 is minimal and not necessarily beneficial.

2017-02-02	Thursday	11:00-3:00	4				Starting to work on the Pantzer stuff. I'm realizing that there might be a good, pipelined way to take a PNG and put it straight to TEI using Tesseract. I first take the PNG and convert it to a HOCR file, which is a simpleHTML file that has every word tagged (it's what used to make a PDF readable). I then clean it up and then do some work on it in XSLT.
2017-02-14	Tuesday	12:00-2:00	2				Further work on Pantzer stuff. Wrote some RegExs to see if whether we can get names tagged. It works to a point, especially since a lot of the names aren't fully separated on different lines in the output. We are getting closer, though.
2017-02-15	Wednesday	2:00-3:00	1				Received email from MH about some problems in primary source rendering. Did some investigating and realized that it's a larger policy issue. Wrote up an explanatory question in Asana to ask at the next team meeting.

2017-02-22	Wednesday	11:00-12:00; 1:15-3:00; 9:30-11:30	4.75	Setting up computer in the new lab and meeting with MH to discuss the diagnostics Oxygen package. Starting some prelimary work on that, creating the GitRepo etc. Got an ANT build up and running and some preliminary XSLT.
2017-02-23	Thursday	12:00-1:00; 10:00-11:00	2	Working on Diagnostics package, moving repos around and playing with Git (I'm still climbing up that learning curve). Working a bit more on the packaging process. The tests on Mariage seem to be going alright.
2017-02-24	Friday	11:00-4:00	5				MoEML meeting. Lots of great discussion for the way forward. One action item is to add a status column
2017-02-27	Monday	9:30-11:30	2	Working on diagnostics package and the file name input. Struggled with this since the editor variable that asks for a URL returns it to ANT in a way that ANT doesn't seem to love—no matter what I tried to do (filepath, etc), it would persistently prepend the diagnostics project directory path to the user's input. The workaround, as far as I can tell, is to set the user's input as a property, thus casting it to a string. Then, using the resourceloader, do some RegEx work on it so that's an easier string for ANT to use and then grab the directory name. The only difficult bit right now is trying to get it so if you put in path/to/my/project (without the final /) it gives you the correct directory (to/my/project) and not to/my. I'm going to say that it's good enough to start working on the XSLT, making that a bit more rigorous

2017-03-01	Wednesday	10:00-11:00	1	Working on diagnostics package, especially adding some better documentation.
2017-03-03	Friday	8:30-10:00	1.5	Diagnostics package: creating the diagnostics div template so that all divs can be consistently created.
2017-03-04	Saturday	11:00-3:00; 5:00-7:30	6.5				Working on the Million words project. First, playing around with MH's hocrToTei conversion from GitHub to see if it might be useful for our purposes. Then working with parsing parentheses in the text, since it's difficult to discern names and other bits of data. I think we're getting to a point now where we can have a near structured list of data with something like what TL did in his DHUM project. Writing some notes trying to figure out how best to structure this data, and investigating linking strategies between EEBO, ESTC, etc. Looking at the TCP GitHubo repo, which is excellent, and figuring out how best to use their data. I think it will really come in handy. Writing a fairly long and detailed email to TL and JJ asking a few questions but also laying out what I've learned over while working through Pantzer's data. Working a bit more on the build process, re-arranging, and trying to tag dates properly (which seems to be working alright).
2017-03-05	Sunday	9:00-10:30	1.5				Fixing a bug in the static_code_documentation code (the ant targets 'quick' and 'subset' were being referenced and link to but they weren't being produced, so the links went no where). Then cruised the static site for a while, trawling for bugs and other inconsistencies. Found a few, particularly in the pages produced from AJAX fragments. Filed those tickets in Asana.
2017-03-06	Monday	6:00-6:30	0.5				Fixing two of the tickets for AJAX fragments: the lack of page footer and date pop-ups.
2017-03-07	Tuesday	7:30-11:00	3.5	Further work on the diagnostics package. Getting the statistics up and running and adding more and more documentation to the file.			Working on fixing up the responsibility_taxonomy page and the taxonomies themselves in PERS1.xml. Had to modify the TEI-simple creation XSLT so that it was valid.